## Filter by Month
2019 Roadmap Rapid Deployment | 2019 Roadmap Rapid Deployment | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
CID Italy
CID Italy | Production Setup | bar: Dec
CID Italy | Go Live | bar: Dec
CID Italy | Support | bar: Dec
CID Italy | Testing (UAT) | bar: Nov
Crossmatch
Crossmatch | Project Preparation | bar: May
Crossmatch | Configuration | bar: Aug to Sep
Crossmatch | Email/Skype | bar: Sep
Crossmatch | OIB - Config | bar: Jul
Crossmatch | OIB - Deploy | bar: Aug
Crossmatch | OIB - Design/Order | bar: May
Crossmatch | Process Definition | bar: Jun to Jul
Crossmatch | Site Assessment | bar: Apr
Crossmatch | Support | bar: Mar
Crossmatch | Testing (UAT) | bar: Dec
Crossmatch | Training (EMEA/APAC) | bar: Nov
Crossmatch | Training (US) | bar: Oct
Crossmatch | AD Migration | bar: Sep
Crossmatch | Telecom | bar: Oct
Crossmatch | Discovery | bar: Feb
Crossmatch | Year End Freeze | bar: Jan
Crossmatch | Go Live | bar: Feb
Demoteller (Facilities)
Demoteller (Facilities) | OIB - Config | bar: Nov
Demoteller (Facilities) | OIB - Deploy | bar: Nov
Demoteller (Facilities) | OIB - Design/Order | bar: Nov
IAI
IAI | Production Setup | bar: Jun
IAI | Project Preparation | bar: Mar
IAI | Email/Skype | bar: May
IAI | Go Live | bar: Jul
IAI | OIB - Config | bar: Mar
IAI | OIB - Deploy | bar: Apr
IAI | OIB - Design/Order | bar: Jan
IAI | Process Definition | bar: Apr
IAI | Site Assessment | bar: Dec
IAI | Testing (UAT) | bar: Jun
IAI | Training | bar: May
IAI | AD Migration | bar: Jun
IAI | Telecom | bar: May
IAI | Support | bar: Aug
Impro / Identitag
Impro / Identitag | Production Setup | bar: Mar
Impro / Identitag | Project Preparation | bar: Nov
Impro / Identitag | Email/Skype | bar: Apr
Impro / Identitag | Go Live | bar: Apr
Impro / Identitag | OIB - Config | bar: Feb
Impro / Identitag | OIB - Deploy | bar: Mar
Impro / Identitag | OIB - Design/Order | bar: Dec
Impro / Identitag | Process Definition | bar: Dec
Impro / Identitag | Site Assessment | bar: Dec
Impro / Identitag | Support | bar: May
Impro / Identitag | Testing (UAT) | bar: Feb
Impro / Identitag | Training | bar: Jan
Impro / Identitag | AD Migration | bar: May
Impro / Identitag | Telecom | bar: Apr
Impro / Identitag | Demo | bar: Nov
Lumidigm (Facilities)
Lumidigm (Facilities) | OIB - Config | bar: May
Lumidigm (Facilities) | OIB - Deploy | bar: Jun
Lumidigm (Facilities) | OIB - Design/Order | bar: Apr
Mercury Security
Mercury Security | Production Setup | bar: Sep
Mercury Security | Project Preparation | bar: Jun
Mercury Security | Email/Skype | bar: Jan
Mercury Security | Go Live | bar: Oct
Mercury Security | OIB - Config | bar: Nov
Mercury Security | OIB - Deploy | bar: Dec
Mercury Security | Process Definition | bar: Jul
Mercury Security | Testing (UAT) | bar: Sep
Mercury Security | Training | bar: Aug
Mercury Security | AD Migration | bar: Feb
Mercury Security | Telecom | bar: Jan
Mercury Security | Discovery | bar: Jun
Mercury Security | Support | bar: Nov
Mercury Security (Facilities)
Mercury Security (Facilities) | OIB - Config | bar: Feb
Mercury Security (Facilities) | OIB - Deploy | bar: Mar
Mercury Security (Facilities) | OIB - Design/Order | bar: Jan
SFDC - CID France
SFDC - CID France | Go Live / Support | bar: Jul
SFDC - CID France | Training/UAT | bar: May
SFDC - CID Galway
SFDC - CID Galway | Go Live / Support | bar: Jul
SFDC - CID Galway | Training/UAT | bar: May
SFDC - CID Hong Kong
SFDC - CID Hong Kong | Go Live / Support | bar: Jul
SFDC - CID Hong Kong | Training/UAT | bar: Jun
SFDC - Peake
SFDC - Peake | Go Live / Support | bar: Feb
SFDC - Peake | Training/UAT | bar: Jan
SFDC - Quantum Secure
SFDC - Quantum Secure | Go Live / Support | bar: Apr
SFDC - Quantum Secure | Training/UAT | bar: Mar

## Pivot Table
Count of Task Name | Column Labels
Row Labels | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
CID Italy
Production Setup | bar: Column Labels Dec
Go Live | bar: Column Labels Dec
Support | bar: Column Labels Dec
Testing (UAT) | bar: Column Labels Nov
Crossmatch
Project Preparation | bar: Column Labels May
Configuration | bar: Column Labels Aug to Column Labels Sep
Email/Skype | bar: Column Labels Sep
OIB - Config | bar: Column Labels Jul
OIB - Deploy | bar: Column Labels Aug
OIB - Design/Order | bar: Column Labels May
Process Definition | bar: Column Labels Jun to Column Labels Jul
Site Assessment | bar: Column Labels Apr
Support | bar: Column Labels Mar
Testing (UAT) | bar: Column Labels Dec
Training (EMEA/APAC) | bar: Column Labels Nov
Training (US) | bar: Column Labels Oct
AD Migration | bar: Column Labels Sep
Telecom | bar: Column Labels Oct
Discovery | bar: Column Labels Feb
Year End Freeze | bar: Column Labels Jan
Go Live | bar: Column Labels Feb
Demoteller (Facilities)
OIB - Config | bar: Column Labels Nov
OIB - Deploy | bar: Column Labels Nov
OIB - Design/Order | bar: Column Labels Nov
IAI
Production Setup | bar: Column Labels Jun
Project Preparation | bar: Column Labels Mar
Email/Skype | bar: Column Labels May
Go Live | bar: Column Labels Jul
OIB - Config | bar: Column Labels Mar
OIB - Deploy | bar: Column Labels Apr
OIB - Design/Order | bar: Column Labels Jan
Process Definition | bar: Column Labels Apr
Site Assessment | bar: Column Labels Dec
Testing (UAT) | bar: Column Labels Jun
Training | bar: Column Labels May
AD Migration | bar: Column Labels Jun
Telecom | bar: Column Labels May
Support | bar: Column Labels Aug
Impro / Identitag
Production Setup | bar: Column Labels Mar
Project Preparation | bar: Column Labels Nov
Email/Skype | bar: Column Labels Apr
Go Live | bar: Column Labels Apr
OIB - Config | bar: Column Labels Feb
OIB - Deploy | bar: Column Labels Mar
OIB - Design/Order | bar: Column Labels Dec
Process Definition | bar: Column Labels Dec
Site Assessment | bar: Column Labels Dec
Support | bar: Column Labels May
Testing (UAT) | bar: Column Labels Feb
Training | bar: Column Labels Jan
AD Migration | bar: Column Labels May
Telecom | bar: Column Labels Apr
Demo | bar: Column Labels Nov
Lumidigm (Facilities)
OIB - Config | bar: Column Labels May
OIB - Deploy | bar: Column Labels Jun
OIB - Design/Order | bar: Column Labels Apr
Mercury Security
Production Setup | bar: Column Labels Sep
Project Preparation | bar: Column Labels Jun
Email/Skype | bar: Column Labels Jan
Go Live | bar: Column Labels Oct
OIB - Config | bar: Column Labels Nov
OIB - Deploy | bar: Column Labels Dec
Process Definition | bar: Column Labels Jul
Testing (UAT) | bar: Column Labels Sep
Training | bar: Column Labels Aug
AD Migration | bar: Column Labels Feb
Telecom | bar: Column Labels Jan
Discovery | bar: Column Labels Jun
Support | bar: Column Labels Nov
Mercury Security (Facilities)
OIB - Config | bar: Column Labels Feb
OIB - Deploy | bar: Column Labels Mar
OIB - Design/Order | bar: Column Labels Jan
SFDC - CID France
Go Live / Support | bar: Column Labels Jul
Training/UAT | bar: Column Labels May
SFDC - CID Galway
Go Live / Support | bar: Column Labels Jul
Training/UAT | bar: Column Labels May
SFDC - CID Hong Kong
Go Live / Support | bar: Column Labels Jul
Training/UAT | bar: Column Labels Jun
SFDC - Peake
Go Live / Support | bar: Column Labels Feb
Training/UAT | bar: Column Labels Jan
SFDC - Quantum Secure
Go Live / Support | bar: Column Labels Apr
Training/UAT | bar: Column Labels Mar

## Sprint Schedule
IT Acquistion Integration - 2019 Sprint Schedule
Acquisition | Task Name | Month | Start | Finish | Status | Resource Names | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
CID Italy
CID Italy | Testing (UAT) | Nov | Mon 4/23/18 | Fri 4/27/18 |  | FIT | Nov: UAT
CID Italy | Production Setup | Dec |  |  |  | FIT | Nov: Prod Setup
CID Italy | Go Live | Dec | Mon 4/30/18 | Fri 5/18/18 | 2018-04-09 | FIT | Dec: Go Live; Jan: Support
CID Italy | Support | Dec | Mon 4/30/18 | Fri 5/18/18 | 2018-04-09 | FIT | Dec: Go Live; Jan: Support
Impro / Identitag
Impro / Identitag | Discovery |  | Mon 11/6/17 | Fri 11/17/17 | CP | Liz,Stan
Infrastructure
Impro / Identitag | Site Assessment | Dec |  |  |  | Zak, Fyzri | Dec: Assess
Impro / Identitag | OIB - Design/Order | Dec |  |  |  | Zak, Fyzri | Dec: O-Design
Impro / Identitag | OIB - Config | Feb |  |  |  | Fyzri | Feb: O-Config
Impro / Identitag | OIB - Deploy | Mar |  |  |  | Fyzri | Mar: O-Deploy
Impro / Identitag | Email/Skype | Apr |  |  |  | Fyzri | Apr: Email
Impro / Identitag | Telecom | Apr |  |  |  | Fyzri | Apr: Telecom
Impro / Identitag | AD Migration | May |  |  |  | Fyzri | bar: May
Business Systems Integration
Impro / Identitag | Project Preparation | Nov |  |  |  | FIT | Nov: Prep
Impro / Identitag | Demo | Nov | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Nov: Demo
Impro / Identitag | Process Definition | Dec | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Dec: Process
Impro / Identitag | Training | Jan | Mon 4/2/18 | Fri 4/20/18 |  | FIT | Jan: Train
Impro / Identitag | Testing (UAT) | Feb | Mon 4/23/18 | Fri 4/27/18 |  | FIT | Feb: UAT
Impro / Identitag | Production Setup | Mar |  |  |  | FIT | Mar: Prod Setup
Impro / Identitag | Go Live | Apr | Mon 4/30/18 | Fri 5/18/18 | 2018-04-09 | FIT | Apr: Go Live
Impro / Identitag | Support | May | Mon 4/30/18 | Fri 5/18/18 | 2018-04-09 | FIT | May: Support
Demoteller (Facilities)
Demoteller (Facilities) | OIB - Design/Order | Nov |  |  | CP | Kiet | Nov: O-Order
Demoteller (Facilities) | OIB - Config | Nov |  |  |  | Kiet | Nov: O-Config
Demoteller (Facilities) | OIB - Deploy | Nov |  |  | 2018-12-01 | Kiet | Nov: O-Deploy
Mercury Security
Mercury Security | Discovery | Jun | Mon 11/6/17 | Fri 11/17/17 |  | Liz,Stan | Jun: Discovery
Infrastructure
| Site Assessment |  |  |  | CP | Kiet
| OIB - Design/Order |  |  |  | CP | Kiet
Mercury Security | OIB - Config | Nov |  |  |  | Kiet | Nov: O-Config
Mercury Security | OIB - Deploy | Dec |  |  |  | Kiet | Dec: O-Deploy
Mercury Security | Email/Skype | Jan |  |  |  | Kiet | Jan: Email
Mercury Security | Telecom | Jan |  |  |  | Kiet | Jan: Telecom
Mercury Security | AD Migration | Feb |  |  |  | Kiet | bar: Feb
Business Systems Integration
Mercury Security | Project Preparation | Jun |  |  |  | FIT | Jun: Prep
Mercury Security | Process Definition | Jul | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Jul: Process
Mercury Security | Training | Aug | Mon 4/2/18 | Fri 4/20/18 |  | FIT | Aug: Train
Mercury Security | Testing (UAT) | Sep | Mon 4/23/18 | Fri 4/27/18 |  | FIT | Sep: UAT
Mercury Security | Production Setup | Sep |  |  |  | FIT | Sep: Prod Setup
Mercury Security | Go Live | Oct | Mon 4/30/18 | Fri 5/18/18 | 2018-10-08 | FIT | Oct: Go Live
Mercury Security | Support | Nov | Mon 4/30/18 | Fri 5/18/18 | 2018-10-08 | FIT | Nov: Support
Mercury Security (Facilities)
Mercury Security (Facilities) | OIB - Design/Order | Jan |  |  |  | Kiet | Jan: O-Design
Mercury Security (Facilities) | OIB - Config | Feb |  |  |  | Kiet | Feb: O-Config
Mercury Security (Facilities) | OIB - Deploy | Mar |  |  | tbd | Kiet | Mar: O-Deploy
IAI
| Discovery |  | Mon 11/6/17 | Fri 11/17/17 | CP | Liz,Stan
Infrastructure
IAI | Site Assessment | Dec |  |  |  | Zak | Dec: Assess
IAI | OIB - Design/Order | Jan |  |  |  | Zak | Jan: O-Design
IAI | OIB - Config | Mar |  |  |  | Zak | Mar: O-Config
IAI | OIB - Deploy | Apr |  |  |  | Zak | Apr: O-Deploy
IAI | Email/Skype | May |  |  |  | Zak | May: Email
IAI | Telecom | May |  |  |  | Zak | May: Telecom
IAI | AD Migration | Jun | bar: Jun
Business Systems Integration
IAI | Project Preparation | Mar |  |  |  | FIT | Mar: Prep
IAI | Process Definition | Apr | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Apr: Process
IAI | Training | May | Mon 4/2/18 | Fri 4/20/18 |  | FIT | May: Train
IAI | Testing (UAT) | Jun | Mon 4/23/18 | Fri 4/27/18 |  | FIT | Jun: UAT
IAI | Production Setup | Jun |  |  |  | FIT | Jun: Prod Setup
IAI | Go Live | Jul | Mon 4/30/18 | Fri 5/18/18 | 2018-07-09 | FIT | Jul: Go Live
IAI | Support | Aug | Mon 4/30/18 | Fri 5/18/18 | 2018-07-09 | FIT | Aug: Support
Lumidigm (Facilities)
Lumidigm (Facilities) | OIB - Design/Order | Apr |  |  |  | Kiet | Apr: O-Design
Lumidigm (Facilities) | OIB - Config | May |  |  |  | Kiet | May: O-Config
Lumidigm (Facilities) | OIB - Deploy | Jun |  |  | tbd | Kiet | Jun: O-Deploy
Crossmatch
Crossmatch | Discovery | Feb | Mon 11/6/17 | Fri 11/17/17 |  | Liz,Stan | Feb: Discovery
Infrastructure
Crossmatch | Site Assessment | Apr |  |  |  | Zak, Fyzri, Kiet | Apr: Assess
Crossmatch | OIB - Design/Order | May |  |  |  | Zak, Fyzri, Kiet | May: O-Design
Crossmatch | OIB - Config | Jul |  |  |  | Zak, Fyzri, Kiet | Jul: O-Config
Crossmatch | OIB - Deploy | Aug |  |  |  | Zak, Fyzri, Kiet | Aug: O-Deploy
Crossmatch | Email/Skype | Sep |  |  |  | Zak, Fyzri, Kiet | Sep: Email; Oct: Email
Crossmatch | AD Migration | Sep |  |  |  | Zak, Fyzri, Kiet | Sep: Telecom; Oct: Telecom
Crossmatch | Telecom | Oct |  |  |  | Zak, Fyzri, Kiet | bar: Oct to Nov
Business Systems Integration
Crossmatch | Project Preparation | May |  |  |  | FIT | May: Prep
Crossmatch | Process Definition | Jun | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Jun: Process; Jul: Process
Crossmatch | Process Definition | Jul | Mon 11/20/17 | Fri 12/29/17 |  | FIT | Jun: Process; Jul: Process
Crossmatch | Configuration | Aug |  |  |  | FIT | Aug: Config; Sep: Config
Crossmatch | Configuration | Sep |  |  |  | FIT | Aug: Config; Sep: Config
Crossmatch | Training (US) | Oct | Mon 4/2/18 | Fri 4/20/18 |  | FIT | Oct: Train
Crossmatch | Training (EMEA/APAC) | Nov |  |  |  | FIT | Nov: Train
Crossmatch | Testing (UAT) | Dec | Mon 4/23/18 | Fri 4/27/18 |  | FIT | Dec: UAT
Crossmatch | Year End Freeze | Jan
Crossmatch | Go Live | Feb | Mon 4/30/18 | Fri 5/18/18 | TBD | FIT
Crossmatch | Support | Mar | Mon 4/30/18 | Fri 5/18/18 | TBD | FIT
Islog | Islog
SFDC - Peake
SFDC - Peake | Training/UAT | Jan |  |  |  | SFDC Consultant | Jan: Train/UAT
SFDC - Peake | Go Live / Support | Feb |  |  |  | SFDC Consultant | Feb: Go Live
SFDC - Quantum Secure
SFDC - Quantum Secure | Training/UAT | Mar |  |  |  | SFDC Consultant | Mar: Train/UAT
SFDC - Quantum Secure | Go Live / Support | Apr |  |  |  | SFDC Consultant | Apr: Go Live
SFDC - CID France
SFDC - CID France | Training/UAT | May |  |  |  | SFDC Consultant | May: Train/UAT
SFDC - CID France | Go Live / Support | Jul |  |  |  | SFDC Consultant | Jul: Go Live
SFDC - CID Hong Kong
SFDC - CID Hong Kong | Training/UAT | Jun |  |  |  | SFDC Consultant | Jun: Train/UAT
SFDC - CID Hong Kong | Go Live / Support | Jul |  |  |  | SFDC Consultant | Jul: Go Live
SFDC - CID Galway
SFDC - CID Galway | Training/UAT | May |  |  |  | SFDC Consultant | May: Train/UAT
SFDC - CID Galway | Go Live / Support | Jul |  |  |  | SFDC Consultant | Jul: Go Live
| Task Name |  | Start | Finish | Status | Resource Names | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec

## Sheet2
IT Acquistion Integration - 2019 Sprint Schedule