## Slide 1
To do:
add department rollout
list separate objectives of key leader vs department
list the qualifications fo the transition eval

## Slide 2: .
.
Stage 1
Executive launch
2 day
meeting audits
leader coaching
Quarterly offsites
Stage 2
Next level rollout
Key leader kickoff
Key leader conferences
Department teams
meeting audits
leader coaching
Objectives
Team cohesion
      Solid trust
  Aligned expectations
Playbook 1.0
Aligned vision, values, strategy, priorities & roles
Productive meetings
Consistent communication with greater org
Department rollouts
Legend
Live off site
video-conference
Objectives
  Key leaders
  Finish Playbook 2.0
  Become Ambassadors of Org Health
  Cross functional cooperation
Department teams
Cohesion, Clarity, productive meetings
Department rollouts
Break down silos
Dept priorities align to org priorities
Transition readiness
Cohesion validation (CTAR)
Playbook complete
Meeting momentum
Transition readiness
Department CTARs
  core values detailed and implemented
meeting mastery
Transition evaluation
Stage 3
Organizational rollout
Playbook rollout
workshops
Training
Internal training
Train the trainers
Train the leaders
Legend
Objectives
  All employees
  Understand and utilize the Playbook
  Are equipped & motivated to create a healthy culture
  The consultation is completed when the leaders are ready to assume responsibility for maintaining a healthy culture.
Transition readiness