## Slide 1
Remote Planning & Scheduling
2020

## Slide 2: Innovative Approach to Planning
No more paying for man hours, buy a finished product
Able to focus on getting the right scope, let us focus on your planning

## Slide 3: RPS Flow Process
Level 1 Schedule
Schedule Review
Level 2 Schedule
Schedule Review
Level 3 Schedule

## Slide 4: Detail Planning
• Conducted field walk & captured field notes
• Collected field photos
• Create job activities, identify resources, estimate durations, identify TA phases
• Annotate pictures and P&ID’s
• Identify blind points (hydro, & entry blinds)
• Identify PPE requirements
• Provide safety ranking for each activity
• Create material list
• Create job packages
• Capture notes at the activity level
• Scaffold Requirements

## Slide 5: Develop Package
• PI&D - mark up scope & blind location
• Plot Plan - mark up scope
• Equip Dwgs – collect add to package
• Equip Data Sheet - collect add to package
• Photo - mark up and scope description
• Safety Data Sheet - identify PPE required
• Step Out - create job step out
• Blind List - create blind list
• Material List - create material list
• QAQC Forms - fill out planning information
• Closure Forms - fill out planning information
• Spec Sheets - order material according to spec
• ITP - incorporate ITP in job plans
• Safety Risk - Identify risk level
• MI Reports - fill out planning information

## Slide 6: Package Review

## Slide 7: Package Acceptance

## Slide 8: Schedules
Level 1
Level 2
Level 3
Schedule Reviews
Internal Logic as well as external logic
Resource leveling
Histograms
Milestone KPI’s
Customized Reporting
Risk Reviewed
Internal Logic only, From one Task to another e.g.… Blind Exchanger to Open Dollar Plate etc.…)
Resource loaded Tasks
Standard Activity Codes assigned to all Tasks
Default Calendars assigned to all Activities (8 hours per day, 5 Days per Week) unless prearranged to use a TAR calendar as the default
All following PMBOK rules for project development

## Slide 9: Remote Planning & Scheduling
Increase efficiency in resource utilization
  Share resources between facilities and events
  Standardize processes across all sites
Build customizable code structures into the job plans
Build safety into each plan
Transparent
Measurable
Accountable

## Slide 10: Remote Planning & Scheduling
Reduce and contain cost of planning
  Reduce/eliminate per diem, overtime
  Reduce headcount on site
  Reduces facilities requirements and safety exposure
Fixed cost per work package/lump sum
Enforces compliance with FEL deliverables
Drive consistency in turnaround processes

## Slide 11: Concept: Using the Best!
Schedulers housed in the KAP corporate office in Houston Texas
Schedulers with access to the latest “Tested” version of Primavera
Schedulers have access to skills training, Primavera/Deltek Acumen FUSE
Schedulers have access to SME’s for schedule “pier asst” at anytime during development of their schedule.
Schedulers with the skill set to host meetings at the site via telecom (video conferencing) software
Schedulers that are certified as Lead schedulers, all the way to Master Schedulers under KAP
Full time or part time schedulers
No travel, No overtime, scalable work hours per week or month

## Slide 12: Savings:
Pay for the time/Package you use
No Per Diem
No Overtime
No Paid Holidays
No Sick Leave
No Vacations Hours
No Taxes
No Insurance
No Risk
No Safety Site Classes and No Background Checks to Perform

## Slide 13: Packages: Planning Phase
Standard Package
  1. Schedule Weekly Progress Report Contains the Following:
    Start Date of Schedule Development
      Assign a Start Data Date
    Number of Worklist Item in Schedule
    Worklist Items in Schedule with Details (Tasks) added
    Logic % Complete
    Worklist Items with Resources and all Activity Codes Progress
    Trended Completion Date

## Slide 14: Packages: Planning Phase
Standard Package:
  Internal Logic only, From one Task to another e.g.… Blind Exchanger to Open Dollar Plate etc.…)
  Resource loaded Tasks
  Standard Activity Codes assigned to all Tasks
  Default Calendars assigned to all Activities (8 hours per day, 5 Days per Week) unless prearranged to use a TAR calendar as the default
  All following PMBOK rules for project development

## Slide 15: Packages: Planning Phase
Advanced Package:
  All the Standard Package items plus:
    Internal Logic as well as external logic
    Resource leveling
    Histograms
    Milestone KPI’s
    Customized Reporting
    Risk Reviewed

## Slide 16: Conclusion:
Remote Planning/Scheduling we save your organization from the headaches and troubles of finding the right person for the right job. Cut your expenses of housing the new employee as well as the reduced overhead cost

## Slide 17: Leveraging the Industries Best
KAP’s office is located in LA Porte, TX, right in the heart of the Petro-Chemical and Refining Industry.
We have access to many of the skilled resources needed for STO planning.
This also eliminates paying per diem cost, no more temporary offices, no more overtime.
Remote Planning also offers fixed prices, now you know how much planning will cost before getting started.

## Slide 18: Keeping Everyone Connected
Remote Planning
Leadership Team
On Site Planner
STOplanner
Remote Planner Team
Complete Work Package
Monitor Progress
Review Content
Track FEL Assignments
Develop Budgets
Share with Stakeholders

## Slide 19
What are the benefits of having a “Remote Scheduler” within your organization?
Reduced cost of operation and higher skilled scheduler…bigger bang for your buck!
Only pay for the amount of work you need
A lead or master scheduler available when you need them
A well structured schedule following your company guidelines
Consistency, your schedules will always be familiar and easy to understand