CAREER-CONNECTED LEARNING IN NEW MEXICO (CCLinNM)

TABLE OF CONTENTS

Page

A.	NEED/SIGNIFICANCE OF PROJECT				  1

A.1	Magnitude of the Need					  1

A.2	Project Significance						  6

A.3	Building Local Capacity					  8

B.	QUALITY OF PROJECT DESIGN				10

B.1	Goals, Objectives, and Outcomes to be Achieved		10

B.2	Research and Effective Practices				13

B.3	Program Dissemination					16

B.4	Innovative Approach to the Priority				16

B.5	Performance Feedback and Continuous Improvement	19

C.	QUALITY OF PROJECT SERVICES				20

C.1	Services Provided						20

Logic Model							32

C.2	Collaboration of Partners					33

C.3	Appropriate to Needs of Intended Recipients			35

C.4	Impact of Services						35

D.	QUALITY OF PROJECT EVALUATION			36

D.1	Methods are Thorough, Feasible, and Appropriate		36

D.2	Performance Feedback/Periodic Assessment of Progress	41

E.	QUALITY OF PROJECT PERSONNEL				42

E.1	Management							42

E.2	Qualifications of Key Staff					45

E.3	Time Commitments						48

F.	ADEQUACY OF RESOURCES					48

F.1	Commitment of Partners					48

F.2	Costs are Reasonable						48

F.3	Incorporation of Project into Agency				49

F.4	Support, Equipment, Supplies, and Other Resources		49

REFERENCES								50

CAREER-CONNECTED LEARNING IN NEW MEXICO (CCLinNM)

A. NEED/SIGNIFICANCE OF PROJECT

A.1	MAGNITUDE OF THE NEED

Two major trends in education today are increasingly influencing school priorities and programs. The first is relevance through a career lens: Schools need to increase their focus on preparing students for postsecondary education options and for work. The second is partnerships: Schools cannot accomplish many of its initiatives for improving student outcomes, particularly in special education, without multi-sector public and private partnerships, resources, and support. Bringing schools and community partners together can produce cooperative career-focused programs that align the realities of the workplace with what students learn in school. When applied to special education, we need “all hands on deck.”

The proposed CCLinNM project introduces Career-Connected Learning (CCL) to special education and as a shared unifying vision across the project’s partnership collaboration. CCL has been shown to be a successful model  for increasing student motivation and engagement by making career exploration and development a core approach to learning. And yet, to date, no implementation of CCL has been adapted for students with disabilities, who also need to prepare for next steps following high-school. In this program, students with disabilities are no longer disregarded but instead can also explore careers of interest and prepare for work.

The reality is that all students, including those with disabilities, are on career pathways, and that all pathways lead to careers. Educators and policymakers are becoming more cognizant of the fact that personalized, relevant programs, such as CCL will address many of the barriers in education that have resulted in systematic exclusion of students with disabilities at an earlier age (Hawley, Cardoso, & McMahon, 2013).  For the state of New Mexico, and as a framework for educational change in districts and states across the country, CCL offers opportunities for major policy impact and systemic change.

The solutions presented in CCLinNM constitute a partnership framework in which students with disabilities explore careers, learn practicable math skills, and gain self-confidence to successfully transition from high school to vocational service supports, postsecondary programs with needed accommodations, or CIE. The shared vision for partners in this project is to embrace CCL as an educational model  leading to competitive independent employment (CIE) where students with disabilities are engaged in work and are treated equally to non-disabled employees (WINTAC, 2016).

A.1.1	Challenges to Equitable Access

Schools face many challenges to ensuring equitable access for students with disabilities. Some of these challenges include inadequate program design and accommodations to help students with disabilities participate; lack of resources in rural areas, which complicates learning; the need for specialized, ongoing training for teachers and community partners working with this population; and identification of business mentors who can help prepare these students for work by sharing what they do at work.

- The proposed CCL digital curricula, Career Exploration and Pathways2 Careers in Math, are nationally recognized CCL curricula used in multiple states. These curricula have formed the foundation of New Mexico’s movement toward career-focused learning, beginning five years ago with Early College High Schools. In 2021-2022, New Mexico made these platforms available to every school district in the state. The goal was to introduce career exploration as a core subject and the CCL math curricula onsite and online to address lack of access to career preparation in remote rural districts statewide. Outcomes to date show increased student proficiencies and understanding of the preparation needed for the careers they chose. While virtual student mentorships and experiences have been incorporated into the Pathways math curricula using Universal Design for Learning, project-based learning, and differentiated instruction, design modifications still are needed to accommodate a more diverse cross-section of students with disabilities.

- Teacher shortages across the state (and the nation) are particularly hard-felt in rural regions of New Mexico, which makes up roughly one-third of the population of the state.  This challenge is being addressed through incentives and outreach to attract teachers to these areas. This need is more critical in the pool of teachers of students with disabilities. Online training and services have abetted this situation, but onsite teachers are essential to support students with disabilities.

- A recent RAND report noted that the lack of communication and sharing between schools, employers, and job-training institutions contributes to the deficiency in student preparation for the changing needs of the workforce (Klein, 2023). When partnership agencies are working in silos and do not share a common vision for how to best prepare these students for work, services are often disjointed.  This program recognizes the imperative to build and nurture partnership collaborations that work together to move outcomes for students with disabilities forward.

- The State of New Mexico has challenges to equitable access across the many remote rural regions in the state. Many students in these areas face food insecurity, poverty, lack of mental and physical health resources, and barriers faced by BIPOC populations. For students with disabilities, these barriers are compounded by the very obstacles they face daily to gain equitable access in learning due to the nature of their disabilities. With a variety of disabilities nationally, spanning 11 categories, the learning needs of this population are diverse. If the learning needs are not met, the result will be little preparation for careers and independent living. These issues of food instability, poverty, and lack of critical supports, particularly in the Navajo Nation in the northern part of the state, have been addressed in several previous initiatives. These issues will continue to be addressed in more depth for this population through the inclusion of more partners.

CCLinNM will confront these challenges through several ways: (1) creation of strong partner networks to support CIE; (2) provision of teacher training on CCL, digital technology, and working with students with disabilities; (3) alignment with state-level standards for Special Education; (4) development of specialized hardware and software to meet the diverse needs of students with disabilities, from mild to severe; and (5) provision of resources provided by New Mexico Public Education Department (NMPED) and their assistive technology support agencies at the request of schools and districts.

Key to meeting these challenges will be a strong program of bi-directional communications conducted through the Project Advisory Board, the project Website, and communication and discourse among partners to ensure everyone is working together.

A.1.2	School Outcomes and Career Exposure

In SY 2022/2023, 50,000 students (16% of the total number of students in New Mexico) qualified for special education services (NMPED website). For these students, low academic proficiency, high dropout rates, and low graduation rates indicate a strong need for major improvement in the quality and effectiveness of education provided to this diverse population group. Two factors stand out among these poor student outcomes: (1) low expectations; and (2) lack of preparation for careers while in school.

Low expectations: Often, little is expected of many students with disabilities. When schools expect less of these students, they acquire lower expectations for themselves and are less likely to participate in the full academic curriculum or advocate for themselves and what they need (Hawley, Cardoso & McMahon, 2013).

Lack of career preparation: Many students with disabilities, once out of high school, have difficulties finding good-paying jobs (Butrymowicz & Mader, 2017). Findings from a national survey of high-school students in special education showed just 15% of students felt their high schools prepared them very well for careers (Lim, 2019). A longitudinal statewide study in the state of Washington found positive outcomes when students with learning disabilities were included in and received career training, with a 4.2% increase in employment, and a 5.7% increase in college enrollment (Theobald, Goldhaber, Gratz, & Holden, 2019).

A.1.3	Relevant Skills for the Workplace

STEM skills are now defining the nature of jobs and being used as a measuring stick for applicants to a job. Students who are not being taught foundational and increasingly more complex math skills are being done a disservice, and this includes students with disabilities. A US News and World Report article suggests most all jobs are STEM, simply because technical awareness, even for entry-level jobs, and problem-solving skills have become mandatory in so many occupations (Soergel, 2015). According to the U.S. Department of Education (2018), math skills are the foundation for students’ future success in STEM careers. Across many of these jobs, minorities and women as well as persons with disabilities, are significantly underrepresented (College Board, 2016; Funk & Parker, 2018). Despite an increased focus on STEM instruction and the growing demand for STEM-trained employees in the workplace, fewer students with disabilities pursue STEM careers.

Preparing for jobs in today’s workplace means learning math. Yet, data from state proficiency testing (on the NMPED website) show students with disabilities had an achievement level in math of just 6%. By providing schools with the proposed CCL math curricula, whose design incorporates differentiated instruction and career content, students who struggle with math can have a second chance to learn at their own pace and build foundational math skills. Differentiated instruction has been proven to support the unique learning needs of students by gearing instruction to their interests, learning styles, and ability levels. This allows students to move freely across levels of instructional support they require (Tiers 1 – 3) (Lusardi, 2017).

A.1.4	 Post-Secondary Statistics

The US Department of Labor (2023) reports the 2022 annual youth labor force participation rate for young people with disabilities, ages 16-19, was 28.9% compared to non-disabled youth (37.2%). The employment gap increased as youth got older: Participation rates for youth 20 to 24 with a disability were 50%, compared with non-disabled youth of the same age (72.1%). (United States Department of Labor, 2033). As these data show, students with disabilities are not successfully transitioning from school to work (Cheng & Shaewitz, 2021).

Non-participation of so many students has local and regional economic impact. In July 2018, just 29% of Americans of working age with disabilities participated in the workforce compared with 75% of Americans without a disability. The impact on our workforce and economy is staggering when considering there are 15.1 million people of working age living with disabilities in the United States. These statistics suggest if companies embrace disability inclusion, they will acquire a new talent pool of more than 10.7 million people. That represents a great opportunity to strengthen businesses and the economy. If just 1% of individuals with disabilities joined the workforce, the GDP could get a boost of up to $25 billion (AAPD, 2018).

A.1.5	Methods to Assess Careers and Special Education

Special education in schools represents a diverse student population that requires individualized services to address unique learning needs. Students’ Individualized Educational Plans (IEPs), revised at least annually, contains specific goals, objectives, strategies, and evaluative measures to determine achievement of outcomes.

When introducing CCL into special education services, new standards for evaluation that use reliable measures will need to be developed to assess progress and incorporated into students’ IEPs.   Measuring growth and outcomes in this area will provide greater direction to transition plans. This is an area that has not been measured before for this population.

A.2	PROJECT SIGNIFICANCE

Never before have students faced challenges from a rapidly changing career landscape as they do today. New jobs are emerging in green industries, health care, and robotics, and other jobs are becoming obsolete due to economic priorities and advancing technological applications. We need to prepare all students, including those with disabilities, for jobs in this changing job landscape (American Institute of Research, 2013). This makes CCLinNM significant: It creates a unifying, shared vision and goals that brings together public agencies, community service providers, and recognized support systems to guide students to jobs and independent living.

This particularly matters for students with disabilities, who have suffered most from the lack of in-school preparation for careers.

A.2.1	Statewide Significance

While New Mexico continues to rank low across measures for state educational outcomes, the state has a long history of innovation and support for career and college readiness. This can be seen clearly in its support for Early College High Schools, career exploration, and teacher professional development. This commitment at the state level distinguishes the state in establishing pathways for improvement.

- In 2020, the state was awarded a demonstration grant from the U.S. Department of Education to introduce career and college readiness courses in schools. Among these courses were the Pathway2Careers math curricula. To ensure equitable access across the state, the courses were made available both online and in-class.

- In 2021, the state was awarded a U.S. Department of Education FIPSE grant to develop career exploration core curriculum for students in grades 6 through 12.

For both of these grants, the innovations were grounded in CCL and made available to districts across the state.

On May 23, 2023, New Mexico again rose to the challenge and has made special education its priority. This May, Governor Grisham issued an executive order to create the Office of Special Education, the first dedicated office of its kind in New Mexico (Office of the Governor, 2023). Operating within the NMPED, the Office is charged with improving the quality of education for the more than 50,000 students with disabilities in the state. With the Executive Order, our proposal herein is well-timed to address the needs and concerns of the State.

A.2.2	National Significance

In 2022, the U.S. Department of Education launched a new initiative specifically to support CCL as a promising practice to help students prepare for careers in today’s high-demand fields and for careers of the future (US Department of Education, 2022). This initiative, in conjunction with the Departments of Commerce and Labor, holds the key to re-engaging students as active agents in their learning; ensuring schools are vital economic drivers in their communities by creating relationships and bridges for students to close the education-to-employment gap; and eliminating workforce shortages. CCLinNM will work to ensure this initiative builds equitable access for all students, including those with disabilities.

Also of national significance and streaming down to the local level, is the support of the U.S. Chamber of Commerce Foundation (USCCF), which developed a framework for employers to use in working with schools to support career development. At its core, these relationships build social capital for students through a network of businesses in need of talent (Kashiri, 2015).  Across New Mexico, the Chambers of Commerce are committed partners to the project (See attached letter of support.)

A.2.3	Growth Measures for CCL and Special Education

CCLinNM is a first-of-its-kind program to engage students with disabilities in career exploration, career development, and CCL in math. The project recognizes the differences in severity of disabilities and types of disabilities to be measured within an umbrella evaluation to produce results that are significant to the field. CCLinNM will focus on growth measures for this population, consistent with the very nature of programming for students with disabilities, which meets the needs of each and every student (and reflected through the IEP.

A.3	BUILDING LOCAL CAPACITY

A key priority for this project is the development of a partnership collaboration with common goals to prepare students with disabilities for next steps following high school. The collaboration will include all stakeholders working with children and youth—including teachers/service providers students, parents, LEAs, the NMPED, the DVR,CILs, prospective employers, and partner universities. First steps to build this coalition will be through the NMPED, which will reach out to its in-place partners who work with children in special education and with special needs. These state partners will be introduced to the project, linked to the Advisory Group and local schools, and asked to bring in their partner network. The link-by-link process will lead to an interwoven support network that builds local capacity.

To reach remote rural communities that have limited resources to support children and youth with disabilities, the ten New Mexico RECs, led by the High Plains REC 1 will take a lead. These RECs, representing 68 primarily rural districts, will work with their member districts to implement the project as a pilot and build local capacity to sustain the changes for students with disabilities. REC staff who have relationships with districts serving impoverished and BIPOC families will ensure all are aware of the project. Large districts—including Albuquerque, Las Cruces, and Santa Fe—will be supported directly by the project leadership and will also participate in the pilot. As this Year 1-2 pilot builds capacity across the state and establishes the strategies and approach for partnerships to help students with disabilities, it will then be expanded and move to the entire state in Years 3 to 5. By the time the project is demonstrated statewide, the local capacity model will be in place for continued expansion.

The State Vocational Rehabilitation Agency (SVRA)—the New Mexico Division of Vocational Rehabilitation (DVR)—is a primary project partner. DVR offices will build local-capacity for transitioning students with disabilities from a CCL-rich academic program to CIE. The DVR’s WIOA funds for pre-employment transition services for high-school students will be a foundational activity. In addition to the pre-employment transition services, the DVR offers vocational counseling and guidance, job searches and placement, and vocational rehabilitation technology. DVR has locations across the state in 17 rural and urban locations. These will work directly with the districts in their service area to participate in CCL in the schools and facilitate the transition of students with disabilities to CIE. This local partnering will build local capacity.

CCLinNM will build partnership networks with the Independent Living Resource Center in New Mexico to support and build local capacity of the 11 Centers for Independent Living (CIL) across the state.  The Resource Center is part of a nationwide disability rights movement through which control is vested in persons with disabilities. The CILs provide advocacy and services to individuals with all disabilities in 16 of the state’s 33 counties, and will build local capacity in those counties.

Consultants for this grant—including NS4ed product and service developer, and Front Porch career video developer—have extensive experience working with education, business, and workforce collaborations. Through their long-standing work across New Mexico with CCL, professional development for educators, and development of online tool kits, their expertise will be used to build local capacity and partnerships around CCL and partnership development.

B.  QUALITY OF PROJECT DESIGN

The proposed project will be made available to all 95 school districts in New Mexico. This includes the largest districts—Albuquerque, Las Cruces, and Rio Rancho as well as the most remote rural districts.

As mentioned previously in this proposal, the NMPED estimates  50,000 students in grades K-12 receive special education services. This project focuses on just those students in 6th through 12th grades to prepare them for careers and CIE. The total enrollment for this grade range in the state in SY 2022/2023 is 174,214. With estimates from the NMPED that 16% of all enrolled students receive special education services, the project potentially will serve 27,874 students (16% of 174,214).

The race/ethnicity of students with disabilities in New Mexico are majority Hispanic/ Latino (58.7%) followed by White (26.2%), American Indian (10.2%), Black (2.1%), and Asian (1.3%). Student outcomes for this population are significantly below those for the general student population: (1) math proficiency levels are just 6%; (2) students in New Mexico with specific learning disabilities account for more than 65% of all out-of-school suspensions; 24% dropped out of school; and 68% graduated (National Center for Learning Disabilities, 2017).

B.1	GOALS, OBJECTIVES, AND OUTCOMES TO BE ACHIEVED

Working with a diverse population of students with disabilities, the project seeks to demonstrate growth across the objectives and outcomes for individual students.

*Project Goal 1: CCLinNM will develop an innovative model of CCL adapted to accommodate students with disabilities.

*Project Goal 2: CCLinNM will demonstrate a multi-sector partnership network made more effective through a unified vision that drives coordinated support services and service delivery models to help transition students with disabilities to postsecondary programs and CIE.

Objective 1:	Increase relevance of course content through education and workforce alignments.

Outcome 1.1:	Labor market sector analyses in New Mexico identify 50 new employers and businesses in the state to partner with education in providing relevance to CCL learning

Objective 2:  Increase access to career exploration tools for students with disabilities to support career planning and successful transitions from high school.

Outcome 2.1: 100% of proposed software will be enhanced with special accommodations for students with disabilities.

Outcome 2.2:  100% of school districts in the state are provided access to the online programs and tools to engage students with disabilities in career exploration activities.

Outcome 2.3: 75% of all students with disabilities discover their job interests and gain the self-confidence to prepare jobs in their chosen field.

Outcome 2.4: 40% of students who view Career Story videos develop mentorship relationships with the employers interviewed.

Objective 3:  Increase motivation to learn and proficiency in math for students with disabilities so they can be prepared for the jobs in the changing workplace.

Outcome 3.1: 100% of software will be enhanced with special accommodations for students with disabilities.

Outcome 3.2: Accommodations to the software increases access and usage of the CCL curriculum by 100% so students can build their math skills.

Outcome 3.3:Math proficiency shows 20% growth for 75% of students with disabilities through differentiated and personalized career-connected learning in math.

Outcome 3.4:  Engagement in school and learning increases through motivation to learn as measured through 25% each in increased attendance, in reduced disciplinary actions, in decreased drop-out rates, and in increased graduation rates.

Objective 4:  Increase self-awareness and self-advocacy skills for students with disabilities.

Outcome 4.1: 50% of students with disabilities demonstrate growth in self-confidence through their Career Page that journals their career interests, celebrates their work in career exploration and CCL math, and documents their progress in preparing for jobs.

Outcome 4.2: 45% of students who develop a Career Page reports a greater sense of their ability to secure meaningful work and advocate for their own needs.

Outcome 4.3 50% of students will self-advocate for needs when working virtually with mentors and prospective employers in the program platform.

Outcome 4.4 75% of students engaged in virtual or on-site internships with prospective employers will communicate needs related to their disability.

Outcome 4.5 75% of students working in CIE will advocate for their needs.

Objective 5: Increase training opportunities for K-12 teachers and partners working with students with disabilities to provide them with a CCL focus from “cradle to careers.”

Outcome 5.1:  80% of teachers report an increased understanding of CCL and the wide-ranging career and work needs of students with disabilities.

Outcome 5.2: 80% of participating teachers report they feel they are more effective working with students with disabilities.

Objective 6: Demonstrate the efficacy of applying a shared vision (CCL) to link educators,  businesses, community stakeholders, economic developers, and state-level agencies in a partnership that coordinates resources and service delivery models for students with disabilities to ease their transition after high school to college and/or CIE.

Outcome 6.1: The project achieves the NMPED and Governor’s goal to develop a comprehensive plan with consistent statewide standards and goals to improve outcomes from “cradle to work” for students with disabilities.

Outcome 6.2: 50 additional business partners across the state will participate.

Outcome 6.3: 20 economic development partners will work with the project to identify areas and career clusters of high work demand.

Outcome 6.4: 75 business partners across the state will provide students with disabilities with onsite and/or virtual work-based learning.

Objective 7:  Increase clarity of measures of CCL in special education.

Outcome 7.1: The project achieves Governor’s goal to develop a comprehensive online data collection system for multiple partners, which aligns with the State Plan and informs evidence-based policies, processes, and programs for students with disabilities.

Outcome 7.2:	Data collection strategies applied to this project are validated and clustered by disability type to more effectively measure growth across a diversified population of students with disabilities.

For the above goals, objectives, and outcomes, quantitative outcomes are measured through growth in math proficiency.  Qualitative outcomes are measured through surveys, focus groups, and questionnaires.

Never before has student growth been linked to growth in career awareness. For this population, growth measures will need to be categorized by types of disabilities, severity of disabilities, and success benchmarks. This will be developed through data collection of each of the partners and the analysis of the aggregated data. More on this is described in the evaluation section of the proposal.

Ongoing data collection will also include level of partner participation (numbers from each entity); number of students (broken down by disability category); and measure of student success, and accessibility. Longitudinal data will be collected through postsecondary sites (colleges) or jobs (DVR).

B.2	RESEARCH AND EFFECTIVE PRACTICES

B.2.1	CCL

While CCL as an educational model has few studies devoted to it holistically, some data analyses and research have been done in areas that reflect the core values of CCL, i.e., the connection of learning with careers. CCL emphasizes purpose, choice, and motivation for students. Hulleman, Barron, Kosovich, & Lazowski, (2015) reviewed current theories and constructs around these assumptions and found they are valuable stimulants to learning.  Perceived value in learning can be critical factors in promoting the desire to acquire new skills (Assor, Kaplan & Roth, 2002; Jang, 2008). Choices in learning can enhance motivation, effort, and persistence in learning (Katz & Assor, 2007; Patall, 2013; Patall, Cooper & Synn, 2010). Purpose in learning has been shown to drive self-regulated learning, which is a valuable goal for students with disabilities (Yeager, Henderson, Paunesku, Walton, D’Mello, Spitzer, & Duckworth, 2014). CCL creates space for these assumptions to take root, and reinforces the importance of partnerships outside the school to reinforce these values.

The following studies show the CCL model used in classrooms by New Mexico, Pathway2Careers. The math curricula have demonstrated strong outcomes and effective practice.

- A 2022 independent study of the effectiveness of Pathway2Careers, conducted by the University of Louisville Center for Research in Mathematics and Science Teacher Development (CRIMSTED), reported notable curriculum strengths including breadth of career integration, rich array of career connections of high interest, incorporation of comprehensive mathematical ideas, and systemic integration of mathematical representations for engaging students (NS4ed, 2022).

- A 2020 pilot study in New Mexico found: (1) 95% of students enjoyed completing the math lessons; and (2) 96% of teachers reported higher student engagement, 83% reported increased interest in career exploration and learning math, and 92% reported higher math performance.

- A 2023 evaluation of career exploration and career-connected math using Pathway2Careers (n=675 students) found more students were considering postsecondary education, training programs to earn industry-approved certifications, and careers in STEM.

Over the past decade, education, the economy, and workforce readiness have converged to redefine what students require from schools. Zinth (2016) attributes these new high-school demands to multiple factors: (1) more jobs and careers require training and education beyond high school; (2) America’s underserved populations have lower probabilities of getting the education and training they need; and (3) traditionally underserved populations constitute a growing proportion of students in US schools. The CCL educational model addresses this trifecta of educational challenges. While CCL can take many forms to accommodate unique needs of different school systems and learners such as students with disabilities, it always requires collaboration with partners from the business community to ensure relevance in learning.

B.2.2	Effective Use for Students with Disabilities

The proposed project proposes the CCL model be adapted for use by students with disabilities. This approach is consistent with the Universal Design for Learning (UDL), which engages students, increases the usability of materials, and improves educational experiences for students with disabilities (Basham & Marino, 2013). Consistent with the three broad principles of UDL, the proposed programs web-based career-connected learning math proposed herein provides multiple means of engagement, representation, actions, and expressions, all which are supportive of special education (Firestone & McMahon, 2021).  Engagement is obtained by considering student preference, built into the program platform as they explore career interests. This commitment to engagement—focusing on student interaction with the content—is critical for students with disabilities, who may lose interest and motivation (Flanagan & Morgan, 2021). This failure to engage students can result in poor performance and few post-secondary opportunities. Through the provision of multiple methods of learning in this program (e.g. library of resources, videos, interactive exercises), students have access to learning through multiple modes. With multiple methods of assessment and teacher support, students can display mastery of content through this online CCL program.

The proposed model also incorporates project-based learning (PBL) in its career-connected math programs where students learn transferrable skills for in and out of school (Larmer, 2016). Taken together, UDL and PBL constitute a constructivist model of teaching and learning where students “construct” their pathway to learning rather than just take in the information. This is often more effective for students with disabilities, where teachers or the students themselves can adjust learning to fit personal needs and accommodations as they learn new information about jobs (Mulcahy & Wertz, 2020).

B.3	PROGRAM DISSEMINATION

A project dissemination plan will be developed by the project Advisory Board during Year 1 of the grant. All dissemination will be coordinated through the NMPED and the newly formed Office of Special Education (OSE).

A detailed Career-Connected Learning for Students with Disabilities Operations Manual will be prepared in the final year and made available to other states and regions wishing to implement a similar program. In addition to a detailed description of steps and timelines for the project, the manual will include research and best practices to support CCL for students with disabilities as well as a list of resources.  The Manual will also be uploaded on the CCLinNM Project Website along with an interactive Toolkit to support implementation. The Toolkit will be a valuable resource for districts in New Mexico during implementation of the project statewide.

Presentations will be made by partners, including students with disabilities, at national, regional, and state conferences to share results and findings from the project. NMPED leadership will also prepare articles for submission to peer-reviewed journals, as well as open access journals, in order to reach a larger audience.

Panels to describe the program, perspectives, and results will comprise all partner groups, with students sharing their stories. These panels will be held regionally, statewide, and nationally. They will also be posted on the Website and can be attended virtually

A separate Story Book will be prepared and disseminated with vignettes from students who participated in this program, from employers who were partners and provided work-based experiences and jobs for the students, and from educators, who can share the positive learning outcomes from the project. The Story Book will also be available through the project website.

B.4	INNOVATIVE APPROACH TO THE PRIORITY

Two intertwined strategies make the project exceptional and an innovative approach.

B.4.1	CCL

Education must assume responsibility for making sure students are college and career ready before they graduate high school. This responsibility dictates that a solid academic and career foundation must be provided for students as they transition from high school to postsecondary careers.

The proposed project encourages intentional decision-making: Career exploration and the CCL math curriculum are introduced in middle school to help students vertically build their math skills. For students with disabilities who need additional time learning math skills and concepts, new software programs that begin earlier than middle-school Pre-Algebra will be  developed, consistent with the current career-focused format. To make this CCL program fully accessible, all accommodations and modifications, including assistive technology, will be incorporated into the program.

The math curricula proposed for this project is relevant, career-connected, and personalized, and follows the Universal Design for Learning. Students receive differentiated instruction, working at their skill level, based on interests and learning styles. A review of the curricula by the NMPED and the OSE will help direct program evaluation accommodations and assistive technology needs.  Teachers will receive the training and support they need to work with students with disabilities in a career-rich classroom environment: (1) through the Webpage; (2) through synchronous webinars; (3) and in-person.

B.4.2	Multi-sector Partnerships

Multi-sector partnerships do not happen organically. Rather, states and districts will need to demonstrate for businesses, community-based organizations, and agencies serving children with disabilities the value of CCL and the role the businesses can play (CCSSO Task Force, 2014). As the CCLinNM partners conduct outreach across their local communities, it is anticipated that businesses and future employers will move beyond a “tacit endorsement” of programs to measures of skills demonstrated (National Career Development, 2020).  Conversations with businesses will help infuse career exploration and math curricula for students with disabilities with input on common duties, knowledge, skills, abilities, and attributes needed to perform specific jobs and minimize skill gaps (Gothberg, Peterson, Peak & Sedaghat, 2015).

B.4.3	Absolute Priority

Through the need and significance (Section A) presented in support of this program, and the goals, objectives, and outcomes above (Section B.1), the project demonstrates a clear understanding of what is expected to meet the grant Absolute Priority. The proposed CCLinNM is an innovative new approach to introducing relevant career preparation into teaching and learning for students with disabilities. Its success requires collaboration between schools, public and private agencies, support teams and others working to ensure this population has the accommodations they need to successfully transition from school to CIE—either directly from high school or after postsecondary education or training. This collaboration is further supported by stakeholders including businesses, parents, support teams, and students who learn to advocate for themselves.

The following requirements of the Absolute Priority are demonstrated herein:

- Partners: Close partnerships including the NMPED, NM DVR, LEAs, CILs, and others providing employment services, training, career exploration, and independent living. Each partner will develop and pilot a cohesive service delivery model built upon CCL, which manages the resources each partner brings to the project. The integration of each partner’s resources is coordinated through the Advisory Board and supported and communicated through the project Website.

- Careers: The unifying model across the collaboration is CCL introduced across the project’s products and services, and which will prepare students with disabilities for the workforce and the opportunity for STEM careers.

- Student expectations: The CCL curricula are driven by students at their own pace to help raise their expectations of what they can achieve. Well-trained teachers and service providers will scaffold instruction to help students gain independence when working in this platform.

- Plan: Working together with the NMPED and the newly formed OSE, the project will participate in building a state-level plan that puts into effect a seamless system of services for students with disabilities

B.5	PERFORMANCE FEEDBACK AND CONTINUOUS IMPROVEMENT

B.5.1	Performance Feedback

The CCLinNM Website will include a stakeholders-access page where those partners working directly with students can upload their qualitative and quantitative data to data collection templates developed as part of the project evaluation design. This design ensures data collection is consistent. By centralizing data collection, the project makes it easier for partners to provide their input and feedback for continuous improvement.

The Advisory Board members working with the evaluator will gather the data and conduct extensive and ongoing data analysis. Preliminary findings will be posted back to the stakeholder data page for sharing. Quarterly reports will be uploaded as well. With this data collection and input design, the project can ensure assessment is built-in and continuous—from baseline, to project data collection. Additionally, qualitative data will be collected by various partners, through focus groups, discussions, and surveys, which are aggregated and posted through the Website.

The project evaluation subcommittee of the Advisory Board will work with NMPED to inventory the extant data points in the state’s Student Information System (SIS) and evaluate the datasets for use with this subset of students. These data will be supplemented with focus groups and surveys with students.

Participating employers, community representatives, and other stakeholder partners will be asked to participate in surveys, focus groups, interviews, and other data collection tools and methods to gain better understanding of the impact of the program on CIE. A two-way feedback loop will be established between delivery sites and the NMPED. When needs are not being met, the appropriate agency, support service, will provide all necessary support and accommodations to enhance student access and success.

In addition to evaluation from the collaboration partners, the Website will be used to gather feedback and continually update parents on project developments. Parents provide valuable input on student growth. A separate page on the Websitewill ask for parent feedback.

B.5.2	Continuous Improvement

Students working within career exploration and CCL math platforms receive continuous feedback, reinforcement, review, and new lessons commensurate to their current learning level. Visuals, picture prompts, and other accommodations will be available to enhance learning and accessibility to content. Student surveys will capture the effectiveness of these approaches.

The Quantile inventory embedded in Pathway2Careers provide immediate performance feedback to students by placing them in lessons commensurate with their ability levels. This is an excellent approach to continuous improvement for students with disabilities. By measuring a student’s readiness to move to the next lesson, the Quantile inventory determines if a student needs more time with a particular skill or concept in mathematics. If so, the system will automatically generate new lessons to engage the student in learning, again demonstrating its ability to be responsive to students of all learning capabilities.

For students who cannot access the content due to the nature of their disability, or who need more time or smaller doses, they can have added supports, provided through program administrators and teachers. An assessment of the barriers will be conducted by schools to specifically pinpoint the barrier(s) and provide accommodations to overcome it (them). Resources and training for teachers and students are available on an ongoing basis to address all unique needs of students with disabilities. This is a strong model for continuous improvement.

`C.  QUALITY OF PROJECT SERVICES

C.1	SERVICES PROVIDED

The CCL services described in this section use the Pathway2Careers platform selected by the NMPED for use throughout the state to help students begin their journeys to careers. Pathways2Careers was first introduced in New Mexico five years ago to support the state’s commitment to Early College High Schools.

The Pathway2Careers CCL model provides a more equitable approach to learning math by making career exploration, which is embedded in the math curriculum and provided as a stand-alone course, the innovative driver for building the foundational interest, engagement, and motivation that will teach students with disabilities how to learn math. Careers are of upmost importance, particularly for those students with disabilities, who often fall through the cracks.

The New Mexico Technology Assistance Program notes that “having accessible web pages is key to providing equal access and information to individuals with disabilities.” Moving forward to expand career exploration and CCL to students with disabilities, the project will work through the NMPED to access digital assistive technology resources for full accessibility.

The following subsections (C.1.1 through C.1.7) describe the products and services that constitute the interventions and strategies used to support goals, objectives, and outcomes (B.1).

C.1.1	Building Relevance through Alignments

The Labor Market Navigator is an easy-to-use, data-rich tool to make all course content relevant. The Navigator translates local market data to educational career clusters aligned with the local economy. School districts are provided a detailed report of the regional labor market to uncover localized career opportunities. By analyzing the labor market profile of the region, the Navigator provides educators with data they need to address unmet needs and skill gaps, to chart career cluster maps and pathways, and to provide a skilled workforce to support economic development in the region. Both regional workforce and educational data are analyzed to help inform education and policy in three main ways:

- District Overview: The Navigator examines demographic information—including population by age, race, and educational attainment.

- Industry Overview:  The Navigator analyzes the top employing industries in those occupations by job roles. Additionally, the Navigator identifies current and future labor needs.

- Career Cluster Analysis: Using the 16 career clusters n the National Career Clusters Framework, the Navigator provides a detailed analysis of the top career clusters and high-value occupations. This includes annual openings, median wages, and projected job growth.

With this information, courses can include relevant data that align with the CIE transition goals of local DVR agencies, schools, and service delivery sites..

C.1.2	Career Exploration

The Pathway2Careers Student Career Exploration system is the first guided, cross-subject curriculum for grades 6-12 in the nation, delivering age-appropriate learning objectives in a connected and cohesive career exploration program. The curricular goal is to expose students to job functions, industries, and careers so they can determine what they are interested in and align their academic course choices with career pathways. Exploration activities for each student are curated all the way through to high-school graduation.

The following chart shows the activities and contents for the Pathway2Careers exploration system, and the grades in which they are introduced. The table reflects grades six through 12. For students with disabilities who may need to begin career exploration at a lower level of engagement, additional activities and lessons will be added in consultation with school counselors and students’ case managers.

|  | Grades |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Learning Objectives/Activities | 6th | 7th | 8th | 9th | 10th | 11th | 12th |
| Complete career interest inventory |  |  |  |  |  |  |  |
| Establish connection to career interest/update |  |  |  |  |  |  |  |
| Re-evaluate career interest inventory |  |  |  |  |  |  |  |
| Complete work values inventory |  |  |  |  |  |  |  |
| Complete work skills inventory |  |  |  |  |  |  |  |

| Learning Objectives/Activities | 6th | 7th | 8th | 9th | 10th | 11th | 12th |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Re-evaluate career interest, work values, and skills inventories |  |  |  |  |  |  |  |
| Explore careers |  |  |  |  |  |  |  |
| Identify top ten careers |  |  |  |  |  |  |  |
| Attend video introduction to careers (local/regional businesses) |  |  |  |  |  |  |  |
| Attend video review of careers and introduction to business opportunities (local/regional businesses) |  |  |  |  |  |  |  |
| Attend video review of careers, with open discussions (local/regional businesses) |  |  |  |  |  |  |  |
| Engage in/continue comparison of careers |  |  |  |  |  |  |  |
| Learn about/review career clusters and identify top career in each career cluster |  |  |  |  |  |  |  |
| Investigate available jobs in interested career clusteTrs |  |  |  |  |  |  |  |
| Learn about Labor Market Information (LMI) |  |  |  |  |  |  |  |
| Learn about alignment of high-value careers among 3 leading indicators |  |  |  |  |  |  |  |
| Review current LMI and current high-value careers |  |  |  |  |  |  |  |
| Engage in career connected learning – supplemental STEM math program (school) |  |  |  |  |  |  |  |
| Begin financial literacy skills development |  |  |  |  |  |  |  |
| Begin soft skills training |  |  |  |  |  |  |  |
| Learn goal setting, resume writing, and interview skills. |  |  |  |  |  |  |  |
| Build academic awareness of fundamental job skills and learning requirements |  |  |  |  |  |  |  |
| Develop degree skill requirements |  |  |  |  |  |  |  |
| Evaluate education and training requirements |  |  |  |  |  |  |  |
| Attend virtual employer visits and/or onsite events |  |  |  |  |  |  |  |
| Explore available summer business opportunities (internship, work study) as introduced by employers in video presentations, and through community partners. |  |  |  |  |  |  |  |
| Explore summer and school-year work-based opportunities (internship, apprenticeship, work study) |  |  |  |  |  |  |  |
| Work with school counselor to map out program of study, aligned to a multi-year IGP including postsecondary education/training or support for CIE. |  |  |  |  |  |  |  |
| Create/update/save portfolio online |  |  |  |  |  |  |  |

Career Stories: An important strategy for increasing career awareness among students with disabilities is through career videos to introduce students to mentors in various occupations. The library currently includes more than 300 15-minute personal narratives from diverse perspectives and brings these real-world working individuals  right into the classroom. In the videos, these employees explain the paths they took to become anything from an architect to an actuary or a bioinformatics scientist to a chemical engineer or a welder. Stories will be introduced by the teachers in the classroom and be available to view again at any time through the video library on the Website.

Each video includes a recording of a person who is successfully employed responding to questions related to the following topics: (a) a brief introduction to the person’s individual background: (2) a personal description of their job requirements; (3) a summary of the person’s career pathway that has led to their current position; (4) a brief summary of each person’s high- school and college experience; and (5) messages of encouragement or a life lesson for students.

For the proposed project, videos will be developed across the state to record local and regional employers in high-demand industries and will contain closed captioning. We anticipate producing 100 new videos in each of Year 1 and 2, many which will feature individuals with disabilities.

Financial Literacy:  Students with disabilities often struggle to make financial decisions and lag behind their peers in developing financial skills. These skills, areas in which they struggle, are essential to transition planning and to achieve economic independence. They include counting money, making and receiving change, engaging in financial transactions, and knowing how to manage and spend money. As students learn how to manage finances, especially in the community setting, they can acquire more independence, which can lead to self-determination and autonomy (Barczak, 2019).

The NMPED and individual LEAs have additional financial literacy courses currently approved. These will be modified to accommodate the varying needs of students with disabilities, and will be incorporated into the career exploration and career-connected math curricula. Modules to teach financial literacy will be on the Website. Synchronous (quarterly) and asynchronous (ongoing) presentations will be available for students on the Website.

The career exploration platform includes embedded financial tools to compare the cost and benefits of the career options and educational pathways they are considering. Information is available on the long-term impact of taking student loans on their financial security, plus entry and mid-career earnings in featured fields. This information is provided by the American Public Education Foundation.

Special Education Enhancements: The curriculum will be modified to include translation of all content to audio and hard copy documents and will use necessary assistive devices to enable access for all students with disabilities. IDEA defines assistive technology as “any item, piece of equipment, or product system, whether acquired commercially off the shelf, modified, or customized, that is used to increase, maintain, or improve the functional capabilities of a child with a disability” (Viner, Shaughnessy, & Singh, 2020). With assistive technology, students with disabilities can gain greater independence, and choose optimum speed of learning, leading to a more personalized learning experience. This is essential to accommodate the many different levels of learning required for students with diverse disabilities. Assistive technology devices may include, but not be limited to Braille embossers, magnifiers, screen readers, screen magnifiers, text readers, speech input software, head pointers, motion or eye trackers, single switch entry devices, wands and joysticks, and alternative keyboards (Dikusar, 2018.

C.1.3	Career-Connected Math

Pathways2Careers, developed through data-driven and evidence-based research, brings careers to life beyond merely teaching math concepts. All lessons are taught within the context of careers so that, at the same time students are learning math, they are learning how it is used in real workplace settings in a variety of careers. Pathway2Careers is unique in that its online digital design enables additions, modifications, and enhancements to lessons to reflect changing demands of the state’s economy (with the Navigator). This makes it easy to show students how math is used in hundreds of jobs with high demand and openings.

All the lessons are aligned with occupations drawn from the 16 career clusters within the National Career Clusters Framework developed by the U.S. Department of Labor.

| - Agriculture, Food, and Natural Resources - Architecture and Construction - Arts, Audio/Visual Technology, and Communications - Business, Management, and Administration - Education and Training - Finance - Hospitality and Tourism - Human Services - Information Technology | - Law, Public Safety, Corrections and Security - Manufacturing - Marketing, Sales, and Service - Science, Technology, Engineering, and Mathematics (STEM) - Government and Public Administration - Health Science - Transportation, Distribution, and Logistics |
| --- | --- |

The web-based math lessons for Pre-Algebra, Algebra I, Geometry, and Algebra II are available online in an interactive program and in PDF form for those who prefer to print the lessons. Two adaptions that will be made to the software reflect these delivery formats—audio for online delivery and Braille for printed PDF files.

Collectively, the Pathway2Careers Math curriculum includes more than 534 lessons introducing students to more than 650 unique occupations. To assure math lessons reflect a student’s career interest, students answer questions about their career interests at the beginning of the course. Based on these responses, the math lessons are personalized to a student’s chosen career cluster.

Lessons are taught in the context of careers. For example, if a lesson is focused on solving problems with angles, it may be taught in the context of an occupation as a carpenter. The lesson shows what carpenters need to know, which courses would be helpful, and how this math is used on the job. Lessons will also include hints for planning how to solve the presented work problem. A series of problems at the end of the lesson determine skill growth and understanding of the math concept taught.

The Career Spotlight (above) is the first page of every application lesson. It includes a description of the occupation, educational requirements, job demand, and salary projections. Career videos can be accessed through this page. Each lesson builds on prior learning by describing the prerequisite learning requirements in the teacher’s editions. For students, the prerequisite skills relate to the spotlighted occupation. This design is especially helpful for students with disabilities, who along with their teacher can determine if they have the prerequisite skills or need to step back to a previous lesson.

On the Job sections which follow present at least four problems directly related to skills and situations that could be found in a particular career, and Practice Problems allow students to demonstrate their proficiency in the skills taught throughout the lesson.

Support for Special Education:  The Pathway2Careers curricula were designed to be responsive to students of differing abilities and learning styles. Much of the program is self-driven. Students take career interest inventories prior to beginning lesson blocks so the computer can generate the math lessons taught in the context of the career cluster the students chose. This design flexibility in the curricula enables students receiving special education services to participate at their own pace, interest, and skill levels.

For students who are challenged by content, lessons can be broken down into sections, and review and reinforcement can be provided after each section. With specialized support for every disability and every student, including all assistive devices and ongoing feedback and modification, students will be able to access the curriculum and show growth.

Overall, the software ensures students are not only motivated, but are working at their comfort and appropriate math academic levels. This is a strong design for students with disabilities. With students moving to Tier II or III, teachers can provide lessons in small groups or individually. This scaffolding is a key element built into the Pathway2Careers math curriculum that supports students with disabilities. If a student with disabilities lacks the very basic skills needed for the pre-algebra lessons, they can be directed to digital training lessons in basic number numeracy and skills. As teachers monitor progress, they can provide needed support to students who may be struggling, by scaffolding, and weaning students from supports when no longer required.

Special Education Adaptations: Specific to this project, Pathway2Careers will make the following adaptations:

- All course content will be translated to an audio presentation and screen readers and Braille will be provided. This will specifically support students with disabilities who are auditory learners, have sight disabilities, or  have dyslexia. These assistive devices will provide greater flexibility and differentiation of instruction for teachers of students with disabilities (Dikusar, 2018). Removing barriers to digital learning through these assistive devices will enhance full accessibility to allow students with disabilities the benefit of the program (Hashey & Stahl, 2014).

- Adhering to the grant’s desire for “cradle to work” support, new content lessons will be developed to accommodate those students with disabilities who need to review and continue to work with foundational math skills. Math lessons will be expanded to include 15 basic math skills lessons introduced through careers, down to the 4th grade to accommodate students with disabilities challenged by the pre-Algebra lessons. These lessons will strengthen addition, subtraction, multiplication, and division skills. Students can continue at this level and strengthen their foundational skills in math for entry-level jobs that require these skills.  Math guide-sheets with teacher recommendations can be provided for students who need to work at a more primary level.

- All math curricula will be converted to HTML in order to incorporate all accommodations for students with disabilities, including those in the career exploration platform and the My Career Page application described following.

C.1.4	My Career Page

The project will introduce students with disabilities to My Career Page, created and updated by students themselves as they explore careers and build their work skills and awareness. Students with disabilities can work on their own or get support from teachers, parents, and counselors as they gradually build these pages that demonstrate their increased knowledge.

My Career Page collects information about what students learned from their career exploration and math lessons. The Career Page includes “journaling,” a way in which students to compose their thoughts about what they have learned about careers or their own aspirations which teacher and counselors may access to provide feedback and personalized guidance. In addition to reflections, the My Career Page electronic portfolio contains career assessment results, cluster matcher results, and favorite or saved careers.

Special Education: The proposed project aims to prepare students in order to successfully transition to CIE after high school. To support this aim, My Career Page will be used by students with disabilities as a “calling card” to secure mentorships, internships, or summer jobs with businesses, either virtually or onsite. Businesses will be able to peruse open areas of the Page to determine if the student’s skills and interests match work-based opportunities the businesses offer.

Special Education enhancements: Students will be able to use speech-to-text software devices to build My Career Page, which will remove barriers for students with dyslexia, dysgraphia, or dyscalculia (three of the most common learning differences teachers encounter) that will impede their progress.

C.1.5  Training and Professional Development

In 2019, only 19% of general education teachers felt prepared to teach students with disabilities, despite the fact that more of 69% of students with disabilities were in general education classrooms more than 80% of the time (Cheng & Shaewitz, 2021). Online and on-site instructional workshops will be provided to teachers, partners, and student support systems to familiarize them with the CCL courses.

Monthly synchronous workshops will be held for all partners to receive training from the Program Director and staff. This training will comprise sample demonstration lessons; evidence-based practices to support students with disabilities; ways to promote and integrate nonacademic skills; how to consider context in teaching; strategies to encourage and motivate students; and focusing on transition supports. Ongoing feedback from participants, through surveys and posts, will drive training to ensure partners have a sense of self-efficacy when using this program. Schedules for each synchronous training session will be posted one month prior to delivery, and can be accessed asynchronously by partners who did not attend a session.

Teachers and service delivery providers will also receive the following training:(1) a detailed scope and sequence summarizes the main topic areas and standards associated with each lesson; (2) the ability to personalize learning through lesson selection and sequencing in the order teachers wish to build skills; (3) teacher outlines and notes accompanying each lesson, and additional notes to guide classroom discussions and learning activities; (4) answer keys and grading rubrics; and (5) access to websites with best-practice reports and research papers to build lesson-related concepts.

A digital library of 20 micro-teaching professional learning lessons will be available to teachers and project partners across the state. Topics include Career-Connected Learning, CCF for Growth and Classroom Assessment, Math Understanding, Career Awareness, Connecting Math Careers to Performance Case Study, and Instructional Strategies for Use in Career-Connected Classrooms.

The project will make its professional development programs (addressing CCL and working with students with disabilities) available to teachers and administrators from K through 12. This ensures those teachers in early elementary school not receiving the direct CCL tools for career exploration and career-infused math will still begin to develop an awareness and understanding of how to prepare students with disabilities for careers after they graduate. It is expected some of these teachers in the lower grades will develop their own career exploration lessons and activities based on the content made available to them in the training.

C.1.6	State Planning and Partnerships

The proposed project administrators will work in tandem the NMPED and newly formed OSE at the fore, providing support and assisting with outreach to stakeholders. Along with the 80 LEAs that will expand Pathways2Careers to students with disabilities, the 11 Centers for Independent Living will invited to partner, develop a service delivery model, and introduce the program at their sites. All partners, including teachers and administrators, will be given access to full participation in the program, with ongoing training and support. The DVR and its local offices will continue its work in fostering prospective employer connections and establishing field placement and internships. Communication with parents, key partners in this program, will include the dissemination of information, access to a newly designed project Webpage, and resources and materials.

In conducting outreach to students with disabilities, the project will aspire to full participation of these students in the program. The very structure of the proposed digital program supports this outreach, with personalized instruction, mentorship, internships, and a wide network of partners working together to reach students with disabilities.

Each partner agency, with its unique services and resources, will develop a service delivery model to harness their resources and support systems and provide seamless, successful transitions to better serve students with disabilities.

A logic model with the inputs, objectives, activities, and short- and long-term outcomes is shown on the following page.

| Project Goal 1: The project will develop an innovative model of CCL adapted to accommodate students with disabilities. Project Goal 2: The project will demonstrate a multi-sector partnership network made more effective through a unified vision of CCL that drives coordinated support services and service delivery models to help transition students with disabilities to postsecondary programs and CIE. |  |  |  |
| --- | --- | --- | --- |
| INPUTS | OBJECTIVE | INTERVENTION (ACTIVITIES) | OUTCOMES |
| Education - NMPED - NM Office of Special Education - NM College and Career Ready Bureau - School districts and schools - Colleges and universities - Regional Education Cooperatives Association Workforce Specialists Local Boards - Comprehensive Local Needs Assessment Boards (10 Boards representing 10 state economic regions) - State Board of Workforce Solutions (representing four regional Boards) Curriculum Developers - NS4ed - Front Porch Studios Bureau of Vocational Rehabilitation Centers for Independent Living | For students with disabilities: - Increase relevance of course content through education and workforce alignments. - Increase access to career exploration tools. - Increase motivation to learn and proficiency in math. - Increase self-awareness and self-advocacy skills. For special education teachers: - Increase training opportunities for teachers to provide them with a CCL focus. For partnership: - Demonstrate the efficacy of applying a shared vision (CCL) to coordinate resources and service delivery models for transition to college and CIE. For evaluation: - Increase clarity of measures of CCL in special education. | - Enhance software with special accommodations. - Develop Advisory Board with diverse partnership, students, and support. - Develop project Website. - Finalize MOUs. - Develop framework/processes for engaging multi-sector partners. - Implement career exploration curriculum with modifications. - Use Career Navigator to gather data and analysis of high-demand jobs. - Develop 15 new CCL math lessons for basic math skills to 4th grade. - Implement CCL math curricula: - Implement modifications. - Develop math guide-sheets with teacher recommendations. - Guide students to build their electronic career portfolio (My Career Page). - Develop career videos with closed captions, with local/regional employers. - Provide a comprehensive professional development program. - Help develop state-level strategy report and data system with policies and practices to serve as models. - Develop guidelines for growth measures of CCL with differing levels and types of disabilities of students. - Develop a NM CCL Operations Manual to guide replication and scale-up. | Short term–students with disabilities - 100% of career exploration and CCL math curricula are enhanced with special accommodations. - 100% of districts provided CCL tools. - 75% of students discover their job interests. - 40% develop mentorships through Career Stories. - Navigator increases relevance of CCL in curricula. - Software accommodations increase access and usage by 100% to build math skills. - Math proficiency shows 10% growth for 75% of students. - Greater engagement: 25% improvement in attendance; disciplinary actions; drop-out; and graduation. - 50% increase self-confidence. - 45% feel they can secure meaningful work and advocate for their own needs. - 50% can advocate for their own needs virtually with mentors and prospective employers. - 75% can communicate needs related to their disability when in virtual and onsite mentorships or internships. - 80% of teachers report higher confidence working with students with disabilities. - 80% of teachers have better understanding of CCL. - Completion of a comprehensive State Plan with consistent statewide standards and goals to improve “cradle to work” outcomes for students with disabilities. - 50 new business partners, 20 economic development partners, and 75 work-based learning opportunities. - Development of a comprehensive data system. - Development of innovative data collection strategies linking special education and careers. Long Term-students with disabilities - 40% of students build STEM math skills aligned to job choices. - 40% of students are prepared for work following graduation. - 75% in CIE will advocate for their needs. - Statewide data system informs evidence-based policies, processes, and programs. - Partnerships continue grow in support of CIE. |

C.2	COLLABORATION OF PARTNERS

Collaboration with all required partners of this grant—the DVR, LEAs, and CILs—will be coordinated through the NMPED, which is the applicant. This sets the development and ongoing operation of the project collaborative at the state level, where the NMPED has existing relationships with each of the partners. Beginning with this high-level partnership collaborative, other stakeholders will be added to the collaborative, including prospective employers, software developers, and community organizations who work on behalf of students with disabilities. As partners are added to the collaborative, the foundation remains strong through NMPED.

One of the major goals for this project supports the New Mexico Governor’s Executive Order 2023-062 to establish the OSE within the NMPED. The EO also called for development of a Consistent Plan of Standards and Goals for Special Education, and a design for collecting data for evidence-based policies and programs. This will be done through the project collaborative, with attached objectives and outcomes to measure success.

As part of the project’s first six months, the collaborative will come together to formalize the state and project’s strategies to support students with disabilities These high-level strategies will ensure the final state plan reflects the contributions and support of each stakeholder group as they work on behalf of career preparation and employment for students with disabilities.

It is the goal of this project to create an environment in which public and private partners actively collaborate to coordinate CCL and the transition of students with disabilities from school to CIE. To meet this goal, the collaborative will work to build new and expanding partnerships with industries and businesses. An innovative approach that will be used for this partnership development is called the “five ships” of stakeholder and employer engagement: leadership, mentorship, internship, apprenticeship, and externship.

- Leadership- This ship gives businesses of any size or industry a voice and influence over what happens in the school and classroom by asking them to share important information such as where the skill gaps are, which jobs are hard to fill, and what credentials and degrees are needed to meet the requirements for these jobs. The U.S. Chamber of Commerce’s Talent Pipeline Management approach is one example of this model. Leadership will also include making employers aware of the availability of students with disabilities to work in their companies and how to best prepare and recruit these students.

- Mentorship-This ship brings business to the classroom or brings the classroom to the business. Students can come face-to-face with employers and worksites virtually through online tours or through the career stories provided in this project. With virtual, real-time tours, employers can interact directly with students, answer questions, introduce worksite teams, and show how some of the machines and operations work.

- Internship-For rural states such as New Mexico, this ship can be achieved through virtual work-based experiences. A most frequent model is through project- or problem-based learning, in which the defined outcome is “instruction.” As teachers and employers partner, students with disabilities can learn about employer expectations and corporate culture, employability skills, and the connection of skills and classroom instruction to what happens in the workplace. Additionally, as students make connections with prospective employers, mentorships and internships evolve.

- Apprenticeship-This ship has a long history in the construction industry but is still new in other industries such as healthcare. Apprenticeships are workforce training that ends with employment and can bring the resources of the local workforce system into collaboration with schools. Partnerships can be effective in providing wrap-around supports to students, which is particularly needed for students with disabilities to obtain CIE.

- Teacher Externship-This ship is an under-utilized tool in building understanding between educators and employers, while also providing educators the knowledge they need to effectively guide students through career-focused learning. Successful teacher externships can become the driver for the other four ships in this model. The hands-on experience of a single educator has scalable impact on students they will encounter in the next year.

C.3	APPROPRIATE TO NEEDS OF INTENDED RECIPIENTS

This program responds to the needs of students with disabilities by offering a career-focused learning experience that includes them in a school’s college and career readiness culture. In this experience, academic skills, career exploration, career development, and mentorship and internship opportunities are melded into a single learning platform. To successfully support students with disabilities through this method, the project’s products and services incorporate problem-solving, work scenarios, and employer presentations into the curricula. Students are motivated as they see the connection between what they are learning, and how it can be used in the workplace. Through project-based learning, students explore, train, and prepare for careers as they grow and learn skills at their ability levels.

Further enhancing student engagement, students with disabilities have the opportunities to build relationships with community and industry specialists, through virtual, onsite, and summer mentorships, internships, and caring connections.

All these components, fully included in this platform, teach students to make informed career decisions, be “better equipped to learn workplace behavior,” and apply these behaviors to the world of work (Ellott & McConnell, 2022).

C.4	IMPACT OF SERVICES

With the CCL model at the center of change, careers are available to all students, particularly those students with disabilities and disengaged, unprepared students who historically have little access to these jobs. Well-designed CCL models in schools can benefit both students and employers by combining classroom learning with meaningful on-the-job work experience (Bierly & Smith, 2022). The impact will be higher number of meaningful jobs for students with disabilities, who will be better prepared for the workplace.

Building upon their developing understanding of their own strengths and interests, their growing confidence in their ability to learn math, and their continuing career exploration, students with disabilities can work with their counselors to set personal goals linked with math and post-graduation options. This is achieved by Pathway2Careers providing: foundational knowledge and skills; evidence-based learning strategies; and choice and purpose in learning.

The goal-setting and reflection continue throughout middle and high school (grades 6 through 12) as students re-take interest surveys; work with counselors to align careers with their course sequences; and gain greater understanding of the link between education and the workplace. Students can store outcomes from the lessons, accompanying activities, assessments, and journal entries in their personal electronic portfolio (Career Page) for ongoing reflection. review, and understanding.

Engaged students who have a vision and a goal are likely to be persistent in their learning, particularly when strategies and innovative, differentiated methods of instruction are designed for success. Ferlazzo (2017) describes engagement as helping students “find their spark and make their own fire.” NS4ed has incorporated the four key elements of engagement, described by researchers as autonomy, competence (self-efficacy), relatedness, and relevance. As educators, our primary role in any approach used is to engage students (Ferlazzo, 2017).

Most important, the impact is in the inclusion of students with disabilities in educational career pathway models, where often they were overlooked because they were “disabled.” With CCLinNM, no student with disabilities is disenfranchised from the workplace and local economy.

D.  QUALITY OF PROJECT EVALUATION

D.1	METHODS ARE THOROUGH, FEASIBLE, AND APPROPRIATE

Baseline: Baseline surveys will be posted on the project Website at the start of the project. These surveys will also be distributed to all partners and to students. Partner surveys will gather information on the services they offer and their delivery model. Student surveys will ask students about any career interests they have, their confidence level with math, and their comfort level communicating their needs.  Baseline data will be gathered from teachers on students’ current math proficiency levels.

These qualitative baseline surveys (with the exception of the teacher quantitative data on math proficiencies) will be designed as 5-point Likert scales, with 1 being least positive and five being most positive. To establish reliability for qualitative measures, interrater reliability will be established. Early in Year 1, three raters in each setting will complete the rubric with a minimum of five students to determine consistency and reliability in responses.

Career Exploration: For career exploration activities, reviews of the curriculum in each grade will be completed bi-annually. Student, counselor, service provider, and teacher surveys will document effectiveness of content and delivery. Surveys will be administered across settings (schools, CIL, DVR offices). Questions will address: (1) how easily students could move through the lessons; (2) how well the content was presented; (3) whether learning was easier when it was linked to careers; (4) how much was learned; and (5) how accommodations to the software helped students (me) use the program;  (6) how students (I) was motivated and excited to learn in this program; (7) how students communicated needs to mentors on program platform;  and (7) pathways reflected a better understanding of college and careers.

Responses will be reviewed by program administrators and the Advisory Board, catalogued, and aggregated to determine any adjustments needed. Findings will be reviewed by the Advisory Board, and posted on the designated program website for all partners to review. Results of these surveys will provide continuous feedback on the program effectiveness and will drive change. These results will be presented as part of the program’s annual report for all stakeholders and policymakers.

Engagement: Additional qualitative measures using the above Likert scale will be conducted through surveys administered to VR service providers to answer the following questions:

- Are students being connected with mentors and prospective employers in their STEM career interest in the community?

- Are students engaging in internships in the community?

- Are students focused on careers through learning as they work within the community?

- Are students demonstrating confidence in participating in community activities?

- Are students able to self-advocate for themselves, communicating needs?

Tracking: The DVR and its local offices will track the number of students with disabilities in the CCL program and their internships or CIE in the community. These numbers will be provided to the Advisory Board and posted on the website. In addition, VR offices will assume the role of following students after they transition from high school. This data collection will be longitudinal to determine the following:

- How many students entered a post-secondary program?

- How many students entered post-secondary STEM program?

- How many students successfully completed STEM programs?

- How many students obtained CIE and how many were in STEM careers?

- How many students received supported, paid employment after high school?

Business partners:

- How many business partners across the sate provide onsite/virtual work experiences?

- How many business partnes identify areas/career clusters of high work demand statewide?

- How many business partners participate in the project?

Job Retention/Success: A follow up will be conducted to determine whether students stayed in their jobs and how successful they felt they were. The longitudinal study will determine the following:

- Are you working in your chosen career (from CCL)?

- Do you feel like you are succeeding in your career?

- Does your employer make modifications to support you?

- Are you able to advocate for yourself and state what you need?

- Are you a part of your community activities?

These surveys can be administered in-person or by phone by VR workers/coaches (yearly), sent to the Advisory Board, and posted on the program website. A rubric will be provided to all SVRAs to complete for students who are currently in the digital CCL STEM program, or for those students who have transitioned from high school to post-secondary settings and careers. These questions and rubrics will be the springboard to discussions of partners in focus groups and in virtual project meetings. In these settings, a member of the Program Advisory Board will be tasked with recording feedback, using the same rubric provided in the survey. This will provide structure and consistency across settings and groups.

Training: Surveys will be provided at the Website to evaluate virtual training workshops for partners. Participants will be encouraged to complete the digital survey online, at the website after the workshop. For those partners accessing workshops asynchronously, surveys will be available at the end of the presentation and will be recorded on the website. Responses will drive future training presentations to meet the needs of all partners. The areas queried following the training, using a 1 to 5 Likert scale are:

- The training provided relevant information to help me in the digital program.

- I am comfortable with the topic presented in this workshop.

- The trainer was clear in presenting information.

- Multiple modes of presentation helped me understand the content.

- This training has given me a better understanding of CCL and work needs of students

- I would recommend this workshop to all partners.

- I am interested to receiving additional training in future workshops.

All findings will also be included in the Operations Manual to support replication and scalability.

The entire proposed project focuses on introducing CCL to students with disabilities to improve their outcomes in school and in securing and retaining jobs. In addition to the data described above, additional data will be gathered to include attendance and disciplinary actions. This feedback will be gathered by individual participating schools and provided to the project for data analysis and continuous improvement.

Quantitative Measures: For math curriculum, carefully crafted assessments have been designed to help students with disabilities self-direct their learning and move forward on the pathways to careers, and teachers can monitor student performance as often as necessary. The Pathway2Careers math curriculum assessments include the embedded Quantile framework, a scientific approach to measuring mathematical achievement and concept/application solvability. Quantile Measures are helpful for linking with the Quantile scores that students earn with lesson objectives. Career information from the O*NET database sets these assessment results in the context of careers—e.g., what preparation is needed. Three unique Quantile assessments are gathered per subject. The three Quantile assessments are spaced out evenly so teachers can administer one assessment at the beginning of year, one in the middle, and one at the end. In this way, students can see their own growth through benchmark results. Teachers can also access performance and growth of individual students, as often as needed (even daily).

Every assessment taken after the first assessment at the beginning of the year also utilizes a Bayesian scoring algorithm to take previous assessment results into account. This ensures that the student’s score becomes more accurate over time. To protect the student in the case of extenuating circumstances, NS4ed’s platform was also built with the ability for teachers or administrators to flag results as invalid and allow students to re-attempt a particular assessment.

To strengthen measures, assessment of skills should be closely aligned with the content of the intervention (Toste, Logan, Shogren, & Boyd, 2023). This platform, implemented with students with disabilities, must consider that validity of these instruments does not exist in isolation, but must take context into account, which includes the diverse communities and schools where students are housed (Talbott, De Los Reyes, Kearns, Mancilla-Martinez, & Wang, 2023). To incorporate context when establishing validity, student data will be broken down by disability categories, and by LEA regions in which they reside. These regions are currently rated, based on rurality, and socioeconomic status. The assessors will be able to pinpoint changes and determine what works, and with who, with a greater level of precision. By including empirical approaches that promote teamwork, collaboration, and community, we better serve our students with disabilities, and engage in evidence-based assessment measures.

D.2	PERFORMANCE FEEDBACK/PERIODIC ASSESSMENT OF PROGRESS

The following model includes three interlocking circles of leadership that strengthen communications and assure feedback and continuous improvement across the grant cycle.

Circle 1: Fiscal and Management Responsibility Members of the CCLinNM Advisory Board will include project management and representatives from each partner group identified to date: NMPED, OSE, Project Manager, Teachers, Students, Parents, CIL representatives,  Chambers of Commerce, IHE, businesses, DVR agencies, RECs, and LEAs.  Membership will be fluid, and if a member drops out, graduates, or leaves a site, replacements will be made to ensure full representation of all partners. The NMPED and OSE will coordinate implementation and monitor activities with all partners and participating schools.

Circle 2: Evaluation and Continuous Improvement.

This circle includes all members of Circle 1, the Advisory Board’s evaluation subcommittee, and the project’s independent evaluator, who willkeep Circle 1 formally apprised of project implementation and impact. Circle 2 will meet monthly. Circle 2 will work closely with partners to determine the impact of the program on academic growth within the program, and non-academic skills (e.g., motivation, comfort, engagement, self-advocacy). Continuous data analysis will drive adjustments to the project on an ongoing basis. Results will indicate and document best practices that were effective in helping students learn, connect to careers, and be motivated on their pathways through high schools, effectively bridging to post-secondary settings, careers, and the community.

Circle 3: School-based Sustainability includes districts, schools, and CILs. Meetings and continuous feedback will be supported through each of the ten RECs and Albuquerque SD, who will provide direct feedback to Circles 1 and 2 to ensure both reviews and steps forward include first-hand accounts of activities and outcomes. Representatives from each REC will have continuous communication with service providers, students, parents, and will have access to the program website to share data and results. The Project Director will meet with the RECs monthly to gather data, aggregate results, and provide input for continuous improvement and vignettes that put a face to career exploration.

These concentric circles of project guidance, management, collaboration, and continuous feedback and improvement will be maintained throughout the project.

The key to ensure success in this project is the strong data assessment and reporting system developed, with data input through the website. Every partner will provide data on student achievement and progress in the program to determine how students are doing and whether they are succeeding in the program. For those students who may be struggling or not gaining program access, a full assessment will be conducted at the local level and sites to determine what barriers are blocking access.

An independent evaluator for the project will work with the Advisory Board, partners, and schools in Circle 2 to support the feedback and continuous improvement process.

E.  QUALITY OF PROJECT PERSONNEL

E.1	MANAGEMENT

The CCLinNM Project Advisory Board will oversee operations and continuous improvement based on lessons learned and input from the independent evaluator. The independent evaluator and Board Evaluation Subcommittee will provide quarterly summaries of findings and communicate insights gained. These summaries will be reviewed in Board meetings where partner input will drive change.

Four Board Subcommittees will be formed to establish a smooth chain of responsibilities and communication, review progress in each area, identify best practices, and suggest enhancements to the project design for continuous improvement in key areas of the project. This will include: Evaluation, Transition, Curriculum and Work-based Learning, and Coalition Building. Meeting schedules will be established by each subcommittee.

The full Board will meet monthly, virtually, through to the end of year 2 and quarterly thereafter. At the start of the project and annually thereafter, onsite Board meetings in a central location will be scheduled.

Timelines for the Project, from Years 1 through 5 are represented below, including inputs, program objectives, activities, and short and middle term objectives.

| Year/Quarter | Activity | Benchmark/Milestone | Responsibility |
| --- | --- | --- | --- |
| Administrative Start-Up |  |  |  |
| Y1, Q1 | Hire Project Manager |  | NMPED |
| Y1 Q1 | Review timelines and activities |  | Advisory Board (AB) |
| Y1, Q1 | Establish Program Advisory Board, with representatives from each partnership group, with at least 10% of representation from students with disabilities | Board will review timelines, activities, assessments, accommodations and provide input others in their partnership group | NMPED |
| Y1 Q1 | Prepare Memorandum of Understanding will all partners as signatories. | Finalized MOU. Signatories; submission to funder within 180 days of award. | AB, Office of Special Education (OSE), Project Co-Director. |
| Y1 Q1-4 | Develop proposed project | Completed plan with strategic benchmarks; pilot-ready | AB, OSE, NMPED |
| Pilot Year 1-2 |  |  |  |
| Y1, Q3 to Y2, Q3 | Begin program pilot | Meetings with pilot sites; monthly reports from sites; student engagement and access. | Project Manager (PM), NMPED, AB, all 10 RECs, Albuquerque LEA; students, parents, support systems |
| Full Implementation Years 3-5 |  |  |  |
| Y2 Q4 to Y5 Q4 ongoing | Refine and implement proposed project. | Program extended to all LEAs in the state; Participation log; data collection logs | PM, NMPED, OSE, RECs, LEAs, teachers, students, parents, support systems, coalition partners. . |
| District Outreach, Partnership Development |  |  |  |
| Y 1, Q 1-4; Y2, Q 1-2 | Work with partners, stakeholders, including districts and schools to plan for system integration | Continuous stakeholder training, resource availability, support provided as springboard to delivery, student work toward development of “My Career Pages” | PM; RECs; NMPED, LEA, CIL, DVR, parents, students |
| Y1, Q2-4 ongoing | Develop service delivery models based upon agency or partner roles | Communication and collaboration between stakeholders | PM, NMPED, partners |
| Y1 Q 1-4 ongoing | Develop mentor/employer videos, to include closed captioning | Assess needs of students with disabilities in designing videos, incorporate strategies, such as video prompts, pauses if needed | Front Porch Studios; PM |
| Y1 ongoing | Establish mentorships and internships, both onsite and online; develop PBL and online simulations and experiences to engage in experiential learning related to careers. | Mentors in existing CCL program will modify PBL experiences, as needed to create access for all students with disabilities | PM, NMPED, RECs, LEA, NS4ed, schools, DVR, prospective employers |
| Implementation of CCL platforms |  |  |  |
| Y1, Q1 | Develop software accommodations. | Expanded curricula to include accommodations | PM, NS4ed, NMPED, OSE |
| Y1, Q1-4 | Connect students to careers through program. | Student access logs. | PM, LEA, RECs, schools, Teachers, Students, Parents, support systems. |
| Y1 Q1 | Extend Pathways math to 4th grade learning level | Development of 15 new lessons. | PM, NS4ed |
| Y1 Q3 ongoing | Conduct growth assessments | Surveys; Quantile scores. | PM, Schools, teachers, partners |
| Years 1, 2, 3, 4, | Assess and provide all assistive technology needed to provide program access for all students with disability participants | Local site evaluations; report of specific needs for assistive technology of each student with disabilities | PM, schools, RECs, LEAs, NMPED, OSE |
| Professional Development |  |  |  |
| Y1 Q1 ongoing quarterly | Develop online professional development programs. | Attendance logs; feedback. | PM, NMPED; AB; RECs, LEAs, schools, teachers, stakeholders |
| Communication and Evaluation |  |  |  |
| Y1 Q1-2 | Develop a project Webpage; develop data collection portal on Website. | Data input; shared data analysis. | PM, NMPED; AB |
| Y1 to Y5 | Collect and analyze project data | Final baseline data gathered through website; collection of data elements | Independent evaluator |

E.1.1  Memorandum of Understanding

Memoranda of Understanding are being developed with partners across New Mexico and will be finalized during the first quarter of Year 1, when the full Advisory Board is constituted and by when the Director of the new OSE will be hired and in place. This intentional delay was done to allow the Board and Office to take a lead and draw upon their current coalitions to develop the larger one that will be effective in this project across every district in the state.

Participants in the Memoranda will include all key staff listed below. The process of developing the Memorandum will be the responsibility of Breezy Gutierrez the Director of College and Career Readiness Bureau. Ms. Gutierrez is the Co-Director of this proposed project, along with Dr. Romero, the Secretary of the NMPED.

Other signatories of the MOU will include the CIL Resource Center; the state-level DVR; the New Mexico Chamber of Commerce; the lead REC for the project, REC #3, Steve Aguirre, Executive Director; all participating districts, and other coalitions partners identified by the Board and Office.

In June 2023, the New Mexico Legislature, Legislative Education Study Committee met to hear a presentation of this proposed project for special education. The Committee was enthusiastic in its support and is providing a letter to that effect. All letters of support are attached to this proposal.

E.2	QUALIFICATIONS OF KEY STAFF

The following key staff will be on the proposed project. Please note, the Project Director, a 100% FTE position, will be hired at the beginning of the project.

Arsenio Romero, Ph.D., Secretary of the NMPED, will serve as the Director of the project, providing 10% of his time. Dr. Romero has more than 25 years’ experience in education as a school and district leader. Prior to assuming the head of the NMPED, he served as superintendent of Los Lunas Schools and superintendent and CEO of Deming Public Schools. Dr. Romero also oversaw district curriculum as assistant superintendent for instruction and transformation for the Roswell Independent School District. He has taught at New Mexico State University since 2014 and joined the NMSU Board of Regents in 2020. Dr. Romero received his Master’s degree and his Ph.D. Degree in Educational Leadership and Administration from University of New Mexico.

Rob Black, JD, President/CEO, New Mexico Chamber of Commerce, the driving force that unites the New Mexico business community. For this project, Mr. Black will be the key liaison with businesses across New Mexico, providing 15% of his time. He is an experienced community relations and public affairs professional with a demonstrated history of grassroots organization, coalition building, and management. Mr. Black received his BA degree in Politics from the University of New Mexico and his JD degree from the University of California, College of the Law, San Francisco.

Breezy Gutierrez, Director of College and Career Readiness Bureau, will serve as co-Director for the project, providing 20% of her time. Ms. Gutierrez earned her BS degree in Biology, Chemistry, and Human Performance from New Mexico Highlands University, and her MS degree in Education from Eastern New Mexico University. Previous to her current position, she was the Deputy Director of College and Career Readiness at NMPED and an Education Administrator.

R. Stephen Aguirre, Executive Director of High Plains REC3, will serve as one of two Regional Support Personnel, providing 15% of his time. Mr. Aguirre leads a progressive and fiscally sound REC, where he initiates projects and services targeting student outcomes based on scientifically based research. He also provides guidance to the region for best practices in education to diverse groups of local schools, teachers, and students. He received his BA degree from Adams State College.

Ricky Williams, NS4ed Director of State Partnerships, will provide full support to the project in developing and implementing strategic plans to support career readiness, providing 40% of his time. Previously, Mr. Williams worked in education across New Mexico for more than 26 years including Superintendent and Director of Secondary Instruction, and was  Superintendent of the Year for New Mexico. He received his BS in Business Administration from Angelo State University (Texas), an MA degree in School Counseling from the University of Texas, and a MS degree in School Administration from the College of Southwest.

Joseph Goins, Ed.D, CEO of NS4ed, will provide program consultation and support for partnership development to the project, providing 15% of his time. For much of his more than 32-year career, Dr. Goins has focused on custom solutions in the education technology industry. This work has enabled him to firmly understand the integration of technology into the classroom settings through resources that promote learner achievement, teacher effectiveness, and leadership strategies for administrators. Dr. Goins earned his bachelor’s degree from Berea College, MS degree in Administration and Supervision from the University of Tennessee, and his Ed.D. in Educational Leadership and Policy from Vanderbilt University.

Tracey Bryan, Director of State Workforce Partnerships, will help coordinate the project and provide support from data management, providing 20% of her time. Ms. Bryan has extensive experience working with communities and states to construct seamless talent pipelines from education to careers in industries vital to economic development. She served as the Chair of the New Mexico State Workforce Board, Southern New Mexico representative on the Business and Advisory Committee of the Federal Reserve Bank of Dallas, and member of the U.S. Chamber of Commerce Business Leads Elite Cohort. She earned her BA degree from Sam Houston State University.

E.2.1	Independent Evaluator

Beverly Kling, Ed.D., Independent Evaluator. Dr. Kling is a retired Special Education Professor at Kean University. During her 28 years at Kean University, Dr. Kling coordinated graduate and certification programs, directed state and national funded grants, and designed courses and university programs in the field of Special Education. As part of the programs, she oversaw program assessments, which included developing rubrics, collecting and aggregating data, and preparing national accreditation reports.  Dr. Kling is the author of multiple articles, a book editor, and has presented at state and national professional workshops. She received a Bachelor’s degree in Elementary Education from Beaver College, her Master’s degree in Special Education from College or New Jersey, and her Ed.D in Special Education with a minor in Supervision from Rutgers University.

E.2.2	Staff to be Hired

Additional staff to be hired by NMPED include: (1) a second Regional Support Personnel will provide 25% of their time; and (2) a full-time Project Manager, for 100% of their time. Both these positions will be hired through the NMPED.

A national search is currently underway for the Director of the Special Education Office formed by the Governor this past month. This office will be within the NMPED.

E.2.3  Equitable Hiring Practices

The program staff is diverse and will continue recruitment of personnel that is representative of all racial, cultural, economic, underrepresented groups. Advertisement of new personnel will be posted at online and local locations, which are visited by diverse groups of candidates. The advertisement will ensure equitable access, with no discrimination.

E.3  TIME COMMITMENTS

All time commitments are noted above with the key staff positions.

F.  ADEQUACY OF RESOURCES

F.1	COMMITMENT OF PARTNERS

As noted across the proposal, there is a strong commitment among partners for the proposed innovative model for transitioning students with disabilities successful to CIE. The Memorandum of Understanding which is being developed (Section E.1.1) will clearly show the commitment of partners, each who is an important resource for the project.

Planning processes for this grant included many of the partners who will have a leadership role in this project including the NMPED, DVR, and RECs.

F.2	COSTS ARE REASONABLE

The budget for CCLinNM is $9,943,500. This budget supports the project delivery for 27,874 students with disabilities across the state of New Mexico’s rural landscape. This calculates to a cost of $356.73 per student over the five years of the grant, or $71.35 per student per year. If participation is at just 70% levels, serving 19,512 students, the costs are still reasonable at $509.61 per student for five years, or $101.92 per student per year.

These costs support the complex development of the partnership coalition, which includes multi-sector service providers and agencies; and service to students with unique disabilities for each individual. Bringing this all together reflect reasonable costs.

The benefits of the project will be gainful employment for students (some in STEM jobs) who may have otherwise been “left out” with traditional projects. As students achieve success, and embark on a pathway to CIE, the costs far offset the gains for stakeholders and students.

F.3	INCORPORATION OF PROJECT INTO AGENCY

The proposed project is being run through the NMPED, Bureau of College and Career Readiness. The project is automatically incorporated into the state agency. Additionally the new Office of Special Education being developed will be through the NMPED as well. This project will be folded into that Office.

F.4	SUPPORT, EQUIPMENT, SUPPLIES AND OTHER RESOURCES

The CCL tools and applications proposed herein are unique in their technology, which integrates into a cloud-based platform: (1) a Learning Management System: (2) a database of 200 separate career-infused mathematics lessons; (3) a descriptive database of career information; (4) an assessment database to measure Quantile changes; and a career database with hundreds of Quantile-measured occupations. For this latter tool, using their Quantile scores, students can review occupations for which they are mathematically prepared to access. The purpose of the database is to provide a critical point of connection for students, allowing them to see how their learning applies to their current and future employment potential.

Technical Compatibility is ensured as students work within the cloud-based program with multiple browsers and wireless LAN. The digital curriculum integrates with numerous LMS systems. Only standard browser plug-ins are required. The program can be accessed through chrome books, Android platforms, or mobile devices.  The digital program is intuitive, as it directs students to lessons, based upon interest and ability level, It also allows students to self-direct their learning, through responses. This digital program allows for identification of individual clients using the application, authenticate the user, ensure rights of user, and enable staff and teachers to track usage and progress.

All support, equipment, and supplies will be provided to the project through the NMPED.

REFERENCES

AIR. (2013 March). Improving college and career readiness for students with disabilities. AIR:

American Institutes for Research. https://files.eric.ed.gov/fulltext/ED555694.pdf.

AAPD. (2018). Getting to equal: The disability inclusion advantage. American Association of

People with Disabilities. https://www.accenture.com/_acnmedia/PDF-89/Accenture-Disability-Inclusion-Research-Report.pdf.

American Institute for Research (2013). How career and technical education can help students

be college and career ready: A primer. www.air.org.

Assor, A., Kaplan, H., & Roth, G. (2002). Choice is good but relevance is excellent: Autonomy

affecting teacher behaviors that predict students’ engagement in learning. British Journal of Educational Psychology, 72(2), 261–278.

Barczak, M.A. (2019). Simulated and community-based instruction: Teaching students with

intellectual and developmental disabilities to make financial transactions. TEACHING

Exceptional Children,51(4), 313-321.

Basham, J.D., & Marino, M.T. (2013). Understanding STEM education and supporting

students through universal design for learning. TEACHING Exceptional Children,

45(4), 8-15.

Bierly, C. & Smith, A. (2022, Jan 25). Taking flight: How to maximize the potential of career-connected learning. Bain & Company. https://www.bain.com/insights/taking-flight-how-to-maximize-the-potential-of-career-connected-learning/.

Butrymowicz, S.; Mader, J. (2017 December 16). The ‘forgotten’ part of special education that

could lead to better outcomes for students. The Hechinger Report. https://hechingerreport.org/forgotten-part-special-education-lead-better-outcomes-students/.

CCSSO Task Force (2014, November). Opportunities and options: Making career preparation

work for students. CCSSO.www.csso.org.

Cheng, L., & Shaewitz, D. (2021). The 2021 youth transition report: Outcomes for youth and young adults with disabilities. Washington, DC: Institute for Educational Leadership. https://files.eric.ed.gov/fulltext/ED617548.pdf.

Daggett, W. R. (2021). The evolution of education: Preparing students for their future (not our past). NY: International Center for Leadership in Education.

Dheesha, J.B. (2021). STEM education to students with special needs. Disabilities and

impairments, 35(1), 28-34. https://www.researchgate.net/publication/363535342_STEM_Education_to_Studentswith_Special_Needs

Dikusar, A. (2018, August 9). The use of technology in special education.

https://elearningindustry.com/use-of-technology-in-special-education.

Ellott, J., & McConnell, A.E. (2022). Navigating remote and virtual work-based learning

experiences for students with disabilities. TEACHING Exceptional Children.

https://doi.org/10.1177/00400599221093085.

Executive Order 2023-062 (2023). Establishing the office of special education within the

public education department. State of New Mexico.

Ferlazzo, L. (2017). Student engagement: Key to personalized learning. Educational

Leadership,74(6), 28-33.

Firestone, J.B., & McMahon, D. (2021). Using technology to provide access to STEM

for students with disabilities. TEACHING Exceptional Children, 55(2), 142-145.

Flanagan, S., & Morgan, J.J. (2021). Ensuring access for all students through universal

design for learning. TEACHING Exceptional Children, 52(6), 459-462.

Gothberg, J.E., Peterson, L.Y., Peak, M., & Sedaghat, J.M. (2015). Successful transition

of students with disabilities to 21st century college and careers: Using

triangulation and gap analysis to address nonacademic skills. TEACHING

Exceptional Children. 47(6), 344-351.

Hashey, A.I.; Stahl, S. (2014). Making online learning accessible for students with disabilities.

TEACHING Exceptional Children. 46(5). 70-78.

Hawley, C.E., Cardoso, E., & McMahon, B.T. (2013). Adolescence to adulthood in STEM

Education and career development: The experience of students at the intersection of

Underrepresented minority status and disability. Journal of Vocational Rehabilitation,

39, 193-204. DOI : 10.3233/JVR-130655.

Hulleman, C.; Barron, K.; Kosovich, J.; Lazowski, R. (2015 January). Student motivation: Current theories, constructs, and interventions within an expectancy-value framework. In:  Psychosocial skills and school systems in the 21st century: theory, research, and practice. Eds: Lipnevich, A.; Preckel, F.; Roberts, R. DOI:10.1007/978-3-319-28606-8_10. https://www.researchgate.net/publication/265966039_Student_Motivation_Current_Theories_Constructs_and_Interventions_Within_an_Expectancy-Value_Framework.

Jang, H. (2008). Supporting students’ motivation, engagement, and learning during an

uninteresting activity. 	Journal of Educational Psychology, 100(4), 798–811. https://doi.org/10.1037/a0012841

Jimenez, L. (2020, Sept 14). Preparing American students for the workforce of the future:

ensuring every student’s readiness for college, career and civic life.

http://www.americanprogress.org/issues/educationo-k-12/reports/2020/09/14/490338/preparing-american-students-  workforce-future/

Kashiri, E. (2015). Connected to careers: Expanding employer leadership in career

development. US Chamber of Commerce Foundation: Center for Education and Workforce. https://www.uschamberfoundation.org/sites/default/files/USCCF_Connected%20to%20Careers_FINAL_0.pdf.

Klein, A. (2019). Teens feel ready for college, but not so much for work. Education Week.

https://www.edweek.org/teaching-learning/teens-feel-ready-for-college-but-not-so-much-for-work/2019/09

Lim, V. (2019, Dec. 12). Students don’t feel their high schools prepare them for careers.

Working Nation. https://workingnation.com/prepare-ri-provides-experiential-learning-students/

New Mexico Office of the Governor. (2023 May 25). Governor creates state’s first Office of

Special Education – State launches national search for leadership. Press Release. Office of the Governor Michelle Lujan Grisham. https://www.governor.state.nm.us/2023/05/25/governor-creates-states-first-office-of-special-education-state-launches-national-search-for-leadership/.

Katz, I., & Assor, A. (2007). When choice motivates and when it does not. Educational

Psychology Review, 19(4), 429–442. https://doi.org/10.1007/s10648-006-9027-y

Kemple, J., & Willner, C. (2008.) Career academies: Long-term impacts on labor market

outcomes, educational attainment, and transitions to adulthood. NY: MDRC.

Larmer, J. (2016). It’s a project-based world. Educational Leadership,73(6), 66-70.

Lusardi, M.L. (2017). Making projects personal. Educational Leadership, 74(6), 46-50.

Meeder, H., & Pawlowski, B. (2020). Preparing our students for the real world: The education

shift our children and future demand. A thought paper for school and community leaders.

National Center for College and Career Transitions (NC3T).

file:///C:/Users/dell/OneDrive/Downloads/Workshop-3-3-Handout-NC3T-Career-Connected-Learning-white-paper.pdf

Mulcahy, C.A., & Wertz, J.A. (2020). Using project-based learning to build college and

career readiness among diverse learners. TEACHING Exceptional Children, 53(5),

341-349.

National Career Development (2020). 2020 virtual career readiness convening summary.

https://docs.google.com/document/d/1B3pYXu7krLc5xN_luMLIjfXuAL0kCgOPBZ6161KlaWs/edit.

National Center for Learning Disabilities. (2017). The State of Learning Disabilities:

Understanding the 1 in 5. New Mexico State Snapshot. https://www.ncld.org/wp-content/uploads/2017/03/New-Mexico.Snapshot.v2.pdf. New Mexico Technology Assistance Program. (nd). Computer accessibility.

https://www.tap.gcd.state.nm/us/accessibility-information/computer-accessibility/.

Patall, E. A. (2013). Constructing motivation through choice, interest, and interestingness.

Journal of Educational Psychology, 105(2), 522–534.

https://doi.org/10/1037/a0030307.

Patall, E. A., Cooper, H., & Wynn, S. R. (2010). The effectiveness and relative importance of

choice in the classroom. Journal of Educational Psychology, 102(4), 896–915.

https://doi.org/10.1037/a0019545

Talbott, E., De Los Reyes, A., Kearns, D.M., Mancilla-Martinez, J., & Wang, M. (2023).

Evidence-based assessment in special education research: Advancing the use of evidence

in assessment tools and empirical processes. Exceptional Children,89(4), 467-487.

Theobald, R.J., Goldhaber, D.D., Gratz, T.., & Holden, K.L. (2019). Career and technical

Education, inclusion, and postsecondary outcomes for students with learning disabilities.

Journal of Learning Disabilities,52(2), 109-119.

Toste, J.R., Logan, J.A.R., Shogren, K.A., & Boyd, B.A. (2023). The next generation of quality

indicators for group design research in special education. Exceptional Children, 89(4),

359-378.

US Department of Labor. (2023). Disability employment statistics. Office of Disability

Employment Policy. https://www.dol.gov/agencies/odep/research-evaluation/statistics.

Viner, M., Shaughnessy, M.F., & Singh, A. (2020). Assistive technology to help students with

Disabilities (Chapter 12). IGI Global.

https://www.igi-global.com/chapter/assistive-technology-to-help-students-with-

disabilities/246671

WINTAC. (2016). Competitive integrated employment. Workforce Innovation Technical

Assistance Center. https://www.wintac.org/topic-areas/resources-and-strategies-competitive-integrated-employment/law-reg-and-policy/5.

Yeager et. al, (2014, Oct). Boring but important: A self-transcendent purpose for learning fosters

academic self-regulation. J Pers Soc Psychol, 107(4), 559-80. doi: 10.1037/a0037637.

PMID: 25222648; PMCID: PMC4643833.

Zinth, J. D. (2016). Policy analysis: Early college high schools: Model policy components.

Education Commission of the States. https://files.eric.ed.gov/fulltext/ED569132.pdf.