## Tabelle1
[8 empty] | Singles Day |  | BlackFriday | Cyber Monday |  |  | Weihnachten
2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
| KW1 | KW2 | KW3
Kickoff: Strategy & Onboarding
Set-up of users, notifications & Panel Konfiguren
Abstimmung Team & Prozesse
Aktueller Marketingplan
Refine Strategie + Prioritäten, Prompt-Tuning
Testrun Kampagnen 28 Tage Q4: First Live Test Runs and Calibratiion
28-day Kampagnen: Capture early holiday demand
Testrun BW Fasttracks 48h
Run BW Fasttracks
Run Weihnachten Fasttrackes
Run 2026-Q1 Marketing
Fully Operational, before BW Start

## Plan detail
[8 empty] | Singles Day |  | Black Friday | Cyber Monday |  |  | Christ-mas | New Year
Task | Work package | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
Kickoff
Company Strategy | bar: 2025-09-29
Background MarketWatch | bar: 2025-09-29
Set-up of users | bar: 2025-09-29
Set-up & fine-tuning of of notifications | bar: 2025-09-29 to 2025-10-06
Panel Konfiguration | bar: 2025-09-29 to 2025-10-06
Alignment Teams & Processes
Aktueller Marketingplan | bar: 2025-10-06
Refine Prioritäten, Prompt-Tuning | bar: 2025-10-06
Prompt-Tuning | bar: 2025-10-06
28-day Campaign Planning
Testing & Calibration | bar: 2025-10-13 to 2025-10-20
Measuring Success | bar: 2025-10-27 to 2025-11-03
Approval
Ongoing Execution | bar: 2025-11-10 to 2025-12-15
Blackweek 2-day Fasttracks
Testing & Calibration | bar: 2025-10-20 to 2025-10-27
| Go Live | 2025-11-03: Fully Operational
| Ongoing Execution | 2025-11-03: Blackweek Fasttracks
Christmas 2-day Fasttracks
Preparation & Calibration | bar: 2025-11-10 to 2025-11-17
| Go Live | 2025-12-01: Christmas Fasttracks
Marketing planning 2026
| Planning 28 + 90 days | 2025-11-17: Marketing Planning 2026
| Execution 28-days | 2026-01-05: Execute
| Execution Fasttracks | 2026-01-05: Execute
Marketing Team workload
| 2-3 Experts (FTE) | 15% | 15% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 75% | 75% | 50% | 15% | 15% | 50%
Aufwand novuter (Std) |  | 12 | 20 | 16 | 16 | 16 | 8 | 8 | 12 | 10 | 8 | 4 | 4 | 4 |  | 8 | 146
[17 empty] | 18.25 | PT

## Plan kompakt (3)
[6 empty] | Singles Day |  | Black Friday | Cyber Monday |  |  | Christ-mas
| week 1 |  | week 3 |  | week 5 |  | week 7 |  | week 8 |  | week 10 |  | week 12
Set-up & Planning
Company Strategy
Background MarketWatch
Set-up of users
Set-up & fine-tuning of of notifications
Panel Konfiguration
Teams & Processes
Aktueller Marketingplan
Refine Prioritäten, Prompt-Tuning
Prompt-Tuning
28-day Campaign Planning
Testing & Calibration
Measuring Success
Approval
Ongoing Execution
Blackweek 2-day Fasttracks
Testing & Calibration
Go Live |  |  |  |  | Fully Operational
Ongoing Execution |  |  |  |  | Blackweek Fasttracks
Christmas 2-day Fasttracks
Testing & Calibration
Go Live | [8 empty] | Christmas Fasttracks
Marketing planning 2026
Planning 28 + 90 days | [6 empty] | Marketing Planning 2026
Execution 28-days | [13 empty] | Execute
Execution Fasttracks | [13 empty] | Execute
2-3 Experts (FTE) | 15% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 75% | 75% | 50% | 15% | 15% | 50%

## Plan kompakt (2)
[7 empty] | Singles Day |  | Black Friday | Cyber Monday |  |  | Christ-mas
| Sept. | October |  |  |  | November |  |  |  | December |  |  |  | Januar
Work package | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
Set-up & Planning
Company Strategy | bar: 2025-09-29
Background MarketWatch | bar: 2025-09-29
Set-up of users | bar: 2025-09-29
Set-up & fine-tuning of of notifications | bar: 2025-09-29 to 2025-10-06
Panel Konfiguration | bar: 2025-09-29 to 2025-10-06
Teams & Processes
Aktueller Marketingplan | bar: 2025-10-06
Refine Prioritäten, Prompt-Tuning | bar: 2025-10-06
Prompt-Tuning | bar: 2025-10-06
28-day Campaign Planning
Testing & Calibration | bar: 2025-10-13
Measuring Success | bar: 2025-10-20 to 2025-11-03
Approval
Ongoing Execution | bar: 2025-11-10 to 2025-12-15
Blackweek 2-day Fasttracks
Testing & Calibration | bar: 2025-10-20 to 2025-10-27
Go Live | 2025-11-03: Fully Operational
Ongoing Execution | 2025-11-03: Blackweek Fasttracks
Christmas 2-day Fasttracks
Testing & Calibration | bar: 2025-11-10 to 2025-11-17
Go Live | 2025-12-01: Christmas Fasttracks
Marketing planning 2026
Planning 28 + 90 days | 2025-11-17: Marketing Planning 2026
Execution 28-days | 2026-01-05: Execute
Execution Fasttracks | 2026-01-05: Execute
2-3 Experts (FTE) | 15% | 15% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 75% | 75% | 50% | 15% | 15% | 50%

## Tabelle2
Opps | Coverage
Unplanned Opportunities: 60% | 60%
Planned Marketing: 40% | 40%

## Plan kompakt
[8 empty] | Singles Day |  | Black Friday | Cyber Monday |  |  | Christ-mas | New Year
Task & Timeline | Work package | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
Kickoff
Company Strategy | bar: 2025-09-29
Background MarketWatch | bar: 2025-09-29
Set-up of users | bar: 2025-09-29
Set-up & fine-tuning of of notifications | bar: 2025-09-29 to 2025-10-06
Panel Konfiguration | bar: 2025-09-29 to 2025-10-06
Alignment Teams & Processes
Aktueller Marketingplan | bar: 2025-10-06
Refine Prioritäten, Prompt-Tuning | bar: 2025-10-06
Prompt-Tuning | bar: 2025-10-06
28-day Campaign Planning
Testing & Calibration | bar: 2025-10-13 to 2025-10-20
Measuring Success | bar: 2025-10-27 to 2025-11-03
Approval
Ongoing Execution | bar: 2025-11-10 to 2025-12-15
Blackweek 2-day Fasttracks
Testing & Calibration | bar: 2025-10-20 to 2025-10-27
| Go Live | 2025-11-03: Fully Operational
| Ongoing Execution | 2025-11-03: Blackweek Fasttracks
Christmas 2-day Fasttracks
Testing & Calibration | bar: 2025-11-10 to 2025-11-17
| Go Live | 2025-12-01: Christmas Fasttracks
Marketing planning 2026
| Planning 28 + 90 days | 2025-11-17: Marketing Planning 2026
| Execution 28-days | 2026-01-05: Execute
| Execution Fasttracks | 2026-01-05: Execute
Marketing Team workload
| 2-3 Experts (FTE) | 15% | 15% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 75% | 75% | 50% | 15% | 15% | 50%