
THE PROVIDENCE BOYNTON COLLECTION
Production Plan & Assembly Guide

PROJECT GOAL
To create a museum-quality presentation that feels like a private exhibition rather than an anniversary gift.
The final presentation should consist of:
1. A Macassar ebony presentation box
1. A museum-quality exhibition portfolio
1. Laura Bergsøe’s handwritten artist note
1. The engraved signature spike
1. Fine art reproductions of the artwork
1. Archival presentation materials
1. Museum-quality assembly
Every element should communicate craftsmanship, restraint, and permanence.

PHASE 1
Materials
Presentation Box
✓ Macassar ebony lacquer presentation box (ordered)

Portfolio
Final Size:
Approximately 11” × 14” portrait (adjust to fit the box if needed).

Printing
Museum-quality archival printing.
Matte finish only.
Pigment inks.
Heavy uncoated paper.
Sewn binding preferred.
Lay-flat if possible.

Interior Materials
Cream archival tissue paper
Black satin ribbon (optional)
Black or charcoal archival photo corners (if mounting handwritten notes)
Archival sleeves (if needed)
Museum-quality mat board (if displaying the spike)
Microfiber gloves for final assembly (optional but recommended)

PHASE 2
Content Collection
Tim
Provide:
□ Personal letter
□ Story of discovering Laura’s work
□ Reflections for each artwork
□ Final approval of all text

Laura
Provide:
□ High-resolution photographs
□ Artist statements
□ Handwritten artist notes
□ Photograph of workshop (if available)
□ Photograph of spike (if available)
□ Certificate of authenticity (if available)

Graphic Designer
Responsible for:
□ Layout
□ Typography
□ Image placement
□ Print-ready files
□ Cover design
□ Production files
□ Printer coordination

PHASE 3
Printing Checklist
Before sending to print:
□ Final proof approved
□ All photographs high resolution
□ Colors reviewed
□ Typography checked
□ Margins reviewed
□ Page numbers verified
□ Spelling verified
□ Bleeds included
□ CMYK exported
□ Print specifications confirmed

PHASE 4
Presentation Assembly
Order of assembly:
Layer One
Cream archival tissue paper

Layer Two
Exhibition Portfolio
Centered inside box

Layer Three
Artist note
Presented in archival sleeve or mounted using archival corners

Layer Four
Engraved signature spike
Displayed separately as:
The First Artifact

Final Inspection
Portfolio clean
No fingerprints
No dust
Spike polished
Handwritten note aligned
Everything perfectly square
Presentation box cleaned

PRESENTATION DAY
Open the box before wrapping.
Confirm:
Everything is aligned.
Portfolio opens correctly.
Nothing shifts when carried.
The experience unfolds in the intended order.

QUALITY CONTROL
Every question should be answered YES.
Does this feel like a museum publication?
Would this feel at home in a Scandinavian museum bookstore?
Does every page breathe?
Does the artwork remain the hero?
Does the experience feel calm?
Would this still feel timeless twenty years from now?
If any answer is “no,” revise before printing.

DELIVERY EXPERIENCE
The recipient should experience the following sequence:
1. Curiosity
1. Discovery
1. Reflection
1. Appreciation
1. Emotion
1. Anticipation
1. Gratitude
No element should interrupt that progression.

PROJECT TIMELINE
Immediately
1. Finalize creative brief
1. Confirm designer
1. Provide source materials
Week One
1. Designer develops concepts
1. Review first layouts
1. Refine typography and pacing
Week Two
1. Incorporate Laura’s handwritten note and spike (if received)
1. Final proof review
1. Send to printer
Final Days Before July 25
1. Receive printed portfolio
1. Assemble presentation
1. Final quality inspection
1. Wrap and prepare for anniversary

FINAL DESIGN PRINCIPLE
The box is not packaging.
The portfolio is not a book.
The spike is not an object.
Together, they tell the story of how extraordinary art becomes part of a home.

One thing I’d add—and I think it may become one of the most meaningful parts of the entire project.
Let’s create a small envelope that stays in the box permanently labeled:
Future Acquisitions
Inside, place a blank archival card that reads:
Acquisition No. 002
Reserved.
It won’t be mentioned during the anniversary. Alvin may not even notice it right away. But months or years later, when you discover another meaningful piece together, you’ll already have the beginning of the next chapter waiting in the box.

