## Slide 1
Project Alignment & Project Communication Process
New Project Identified
Governance Meeting
Separate Project Meetings as needed
Governance Meeting
Weekly Center Leader Meeting
Field Advisory Panel
Purpose: Collect Feedback
When: As needed
Weekly Center Leader Meeting
Purpose: Center Planning and Specific execution details
When: 1 month out
Monday Memo
1 week out
Follow Up Guide
Post Launch
Daily Digest
Just in Time Notice/Follow up for execution
Planning & Design Phase
Prepare Phase
Follow Up & Evaluate
Purpose: Go/No Go Decision
3 + Months out
2+ months out
1 month out
1 Week out
Overview: Project Owner presents one pager to Sr Leadership. Based on Business Value, and Capacity a Go/No Go Decision is made.
Purpose: Report out on Milestone status and Key Decision Points
Overview: Project Owner presents milestones and feedback/approvals during key decision points.
Purpose: Introduce Project & gather Center Leader Feedback
Overview: Project Owner provides overview of project, collects center leader feedback.
Purpose: Collect Center Staff Feedback
Overview: Project Owner presents project and collect Center Staff Feedback
Purpose: Provide Center Leaders with Implementation Details
Overview: Project Owner presents project and implementation details to ensure Center Leaders are prepared.
Meetings
Emails/Tools